## Consolidated Master (All)
Zoho Projects Implementation — Consolidated Master Task Sheet
Complete master registry of all 95 discrete implementation tasks across Basic (26h), Professional (63h), and Elite (115h) tiers.
Plan Tier | Product | Module | Module Description | Feature | Feature Description | Parent Task | Parent Task Description | Sub-Task | Sub-Task Description | Estimation Hours | Type | Complexity | Best Case Hours | Worst Case Hours | Deliverables | Prerequisites | Client Input | Script | Depends On | Dependency Type
Basic | Zoho Projects | Organization & Portal Setup | Initial enterprise portal provisioning, branding, regional work calendar, time zone, and transactional email configuration. | Portal & Global Configuration Setup | Foundational portal settings governing all project timelines, operating hours, and system-wide communications. | Portal Setup & Global Settings | Global configuration of portal branding, regional calendar, and delivery notifications. | Portal Profile & Branding | Configure company name, portal logo, favicon, base currency, and default date/time format across the Zoho Projects workspace. | 1.00 | Configuration | Low | 0.80 | 1.20 | Configured branded portal with corporate logo, favicon, and regional date/time standards. | Corporate logo, base currency, and time zone details provided. | Yes | No
Basic | Zoho Projects | Organization & Portal Setup |  | Portal & Global Configuration Setup |  | Portal Setup & Global Settings |  | Work Calendar, Timezone & Operating Hours | Define standard organization working days, shift hours, and weekly off days to anchor scheduling and SLA timers. | 1.00 | Configuration | Low | 0.80 | 1.20 | Operating calendar active with official working days and business hours established. | Weekly operating schedule confirmed. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Basic | Zoho Projects | Organization & Portal Setup |  | Portal & Global Configuration Setup |  | Portal Setup & Global Settings |  | Default Notification Preferences & Email Setup | Set up default email notification digests, project alerts, and system-wide communication preferences for internal users. | 0.50 | Configuration | Low | 0.40 | 0.80 | Standardized notification matrix preventing alert fatigue. | Internal notification rules agreed. | No | No | Portal & Global Configuration Setup › Work Calendar, Timezone & Operating Hours | Requires
Basic | Zoho Projects | User Roles & Access Permissions | Role-based access control, standard user profiles, user onboarding, and internal data security boundaries. | User Administration & Role Governance | Establish access boundaries, user licenses, and data visibility rules across project teams. | User Management & Role Matrix | Configure standard profiles, user invitation pipelines, and access boundaries. | User Profiles & Standard Role Matrix | Configure standard role permissions (Admin, Manager, Employee, Contractor) defining view, edit, and delete rights. | 1.00 | Configuration | Medium | 0.80 | 1.50 | Approved standard role permission matrix active in Zoho Projects. | Organizational staffing matrix provided. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Basic | Zoho Projects | User Roles & Access Permissions |  | User Administration & Role Governance |  | User Management & Role Matrix |  | User Onboarding & Profile Assignment | Invite and provision initial core team members, assign designated roles, and verify profile-level permissions. | 1.00 | Configuration | Low | 0.80 | 1.20 | Core user team onboarded with active portal access. | User email list and role mappings provided. | Yes | No | User Administration & Role Governance › User Profiles & Standard Role Matrix | Requires
Basic | Zoho Projects | User Roles & Access Permissions |  | User Administration & Role Governance |  | User Management & Role Matrix |  | Data Access & Security Boundaries | Establish project-level visibility rules ensuring team members only access projects and deliverables assigned to them. | 0.50 | Security | Low | 0.40 | 0.80 | Confidential data isolation verified across sample user accounts. | Project confidentiality policy defined. | No | No | User Administration & Role Governance › User Onboarding & Profile Assignment | Requires
Basic | Zoho Projects | Project Structure & Grouping | Organizational portfolio taxonomy, project groups, and master tag categorization. | Portfolio Taxonomy & Categorization | Logical structure grouping client projects by department, industry vertical, or commercial status. | Project Grouping & Taxonomy | Creation of portfolio groups and tagging taxonomy. | Project Groups & Master Tag Library | Set up project groups (e.g., Internal, Client Engagements, R&D) and create standardized master tag library for cross-project filtering. | 1.00 | Configuration | Low | 0.80 | 1.20 | Master tag library and portfolio group categories active. | Departmental taxonomy approved. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Basic | Zoho Projects | Project Structure & Grouping |  | Portfolio Taxonomy & Categorization |  | Project Grouping & Taxonomy |  | Client Association & Tags | Establish client company profiles within Zoho Projects and link client accounts to corresponding active project workspaces. | 1.00 | Configuration | Low | 0.80 | 1.20 | Initial client account directory linked to corresponding project groups. | Client company list provided. | Yes | No | Portfolio Taxonomy & Categorization › Project Groups & Master Tag Library | Requires
Basic | Zoho Projects | Standard Project Template Architecture | Creation of standardized project templates, repeatable task lists, and Rapid project provisioning. | Project Template & Delivery Standardization | Turnkey templates codifying standard operating procedures for rapid, consistent project kickoffs. | Template Engineering & Instantiation | Build and calibrate master project delivery templates. | Master Project Template Creation (Up to 5) | Build up to 5 standardized project delivery templates with pre-configured milestones, task lists, and recurring deliverables. | 1.50 | Configuration | Medium | 1.20 | 2.00 | 5 production-ready project templates configured in the template gallery. | Standard WBS deliverable flows provided. | Yes | No | Portfolio Taxonomy & Categorization › Project Groups & Master Tag Library | Requires
Basic | Zoho Projects | Standard Project Template Architecture |  | Project Template & Delivery Standardization |  | Template Engineering & Instantiation |  | Task List Standardization & Plain/Kanban Views | Configure task list categorization and optimize Classic, Plain, and Kanban board task views within standard templates. | 1.00 | Configuration | Low | 0.80 | 1.20 | Standardized task lists with customized Kanban board columns. | Task status definitions agreed. | No | No | Project Template & Delivery Standardization › Master Project Template Creation (Up to 5) | Requires
Basic | Zoho Projects | Standard Project Template Architecture |  | Project Template & Delivery Standardization |  | Template Engineering & Instantiation |  | Template Cloning & Instantiation | Validate template-to-project creation workflow, ensuring tasks, milestones, and assigned roles clone accurately upon instantiation. | 0.50 | Validation | Low | 0.40 | 0.80 | Successful test instantiation of a live project from master template. | Templates completed. | No | No | Project Template & Delivery Standardization › Task List Standardization & Plain/Kanban Views | Requires
Basic | Zoho Projects | Task Breakdown Structure (WBS) & Milestones | Decomposition of complex client contracts into milestones, parent tasks, and sub-tasks with percentage progress rollups. | Work Breakdown Structure (WBS) Engine | Multi-tier deliverable decomposition ensuring complete milestone traceability. | WBS & Milestone Planning | Structure milestones, nested subtasks, and progress tracking. | Milestone & Phase Configuration | Establish project milestones linked to deliverable target dates, designated milestone owners, and flag milestone completion criteria. | 1.00 | Configuration | Low | 0.80 | 1.20 | Milestone timeline established across sample delivery project. | Target deliverable dates defined. | Yes | No | Project Template & Delivery Standardization › Template Cloning & Instantiation | Requires
Basic | Zoho Projects | Task Breakdown Structure (WBS) & Milestones |  | Work Breakdown Structure (WBS) Engine |  | WBS & Milestone Planning |  | Task & Nested Subtask Hierarchy | Configure multi-level nested subtasks under primary deliverable tasks with automatic progress percentage rollups to parent tasks. | 1.00 | Configuration | Medium | 0.80 | 1.50 | Multi-tier task hierarchy active with dynamic percentage rollups. | Nested task breakdown agreed. | No | No | Work Breakdown Structure (WBS) Engine › Milestone & Phase Configuration | Requires
Basic | Zoho Projects | Task Breakdown Structure (WBS) & Milestones |  | Work Breakdown Structure (WBS) Engine |  | WBS & Milestone Planning |  | Task Priority, Tags & Recurrence | Setup priority flags (None, Low, Medium, High), task recurrence schedules, and tag assignments for operational sorting. | 0.50 | Configuration | Low | 0.40 | 0.80 | Priority and recurring task schedules active. | Recurrence intervals provided. | No | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Basic | Zoho Projects | Task Dependencies & Gantt Visualization | Chronological Gantt chart configuration, predecessor dependency logic, and dynamic schedule cascading. | Gantt Timeline & Predecessor Logic | Visual chronological scheduling ensuring tasks execute in contractual sequence. | Gantt Scheduling & Dependency Linking | Set up Gantt charts, FS dependency logic, and timeline cascading. | Finish-to-Start (FS) Dependencies | Configure standard Finish-to-Start (FS) dependency links between predecessor and successor tasks across project task lists. | 1.00 | Configuration | Low | 0.80 | 1.20 | Predecessor-successor links active across task timelines. | Deliverable sequence logic confirmed. | No | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Basic | Zoho Projects | Task Dependencies & Gantt Visualization |  | Gantt Timeline & Predecessor Logic |  | Gantt Scheduling & Dependency Linking |  | Chronological Gantt Chart View & Export | Configure chronological Gantt timeline display, milestone markers, dependency lines, and PDF/image export options. | 1.00 | Configuration | Low | 0.80 | 1.20 | Interactive Gantt view verified with working PDF export. | Tasks and dependencies populated. | No | No | Gantt Timeline & Predecessor Logic › Finish-to-Start (FS) Dependencies | Requires
Basic | Zoho Projects | Task Dependencies & Gantt Visualization |  | Gantt Timeline & Predecessor Logic |  | Gantt Scheduling & Dependency Linking |  | Schedule Cascading Verification | Test and verify dynamic date shifting: ensure that extending a predecessor task deadline automatically shifts dependent successor dates. | 0.50 | Validation | Low | 0.40 | 0.80 | Dynamic date cascading verified with zero scheduling breaks. | Gantt dependencies active. | No | No | Gantt Timeline & Predecessor Logic › Chronological Gantt Chart View & Export | Requires
Basic | Zoho Projects | Timesheets & Work Logging | Time tracking, live stopwatch timer, daily/weekly timesheet grids, and basic approval workflows. | Time Tracking & Timesheet Logging | Captures staff execution hours against tasks and milestones for operational auditing. | Timesheet Configuration & Work Logging | Configure time logging grids, timers, and manager review. | Daily & Weekly Timesheet Logging | Configure timesheet entry grid allowing team members to log actual work hours against tasks with mandatory activity notes. | 1.00 | Configuration | Low | 0.80 | 1.20 | Timesheet grid operational with daily/weekly view options. | Time tracking policy established. | Yes | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Basic | Zoho Projects | Timesheets & Work Logging |  | Time Tracking & Timesheet Logging |  | Timesheet Configuration & Work Logging |  | Live Stopwatch Timer & Billable Classification | Configure desktop and mobile in-app live stopwatch timers and configure Billable vs Non-Billable hour categorization. | 0.50 | Configuration | Low | 0.40 | 0.80 | Live timer functional with billable status flags. | Billable criteria defined. | No | No | Time Tracking & Timesheet Logging › Daily & Weekly Timesheet Logging | Requires
Basic | Zoho Projects | Timesheets & Work Logging |  | Time Tracking & Timesheet Logging |  | Timesheet Configuration & Work Logging |  | Standard Timesheet Approval Flow | Set up project manager timesheet review workflow allowing PMs to approve, edit, or reject submitted time logs prior to closing. | 1.00 | Configuration | Medium | 0.80 | 1.20 | Managerial timesheet approval queue active. | Approval hierarchy agreed. | Yes | No | Time Tracking & Timesheet Logging › Live Stopwatch Timer & Billable Classification | Requires
Basic | Zoho Projects | Documents, Zoho Meeting & File Repository | Project documentation repository, document versioning, and Zoho collaboration app interconnect. | Document Storage & Meeting Collaboration | Centralized project asset repository and integrated virtual meeting tools. | Document Repository & Collaboration Tools | Structure folders, document versions, and virtual meetings. | Project Folder & Document Hierarchy | Configure structured project document folder hierarchy (e.g., Deliverables, Meeting Notes, Client Specs) for file centralization. | 1.00 | Configuration | Low | 0.80 | 1.20 | Standardized folder structure embedded across project workspaces. | Folder taxonomy approved. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Basic | Zoho Projects | Documents, Zoho Meeting & File Repository |  | Document Storage & Meeting Collaboration |  | Document Repository & Collaboration Tools |  | File Uploads, Previews & Version History | Configure file attachment rules, inline document previewing, and document version history tracking on tasks and project docs. | 1.00 | Configuration | Low | 0.80 | 1.20 | File versioning verified with multi-format previews. | File storage policy confirmed. | No | No | Document Storage & Meeting Collaboration › Project Folder & Document Hierarchy | Requires
Basic | Zoho Projects | Documents, Zoho Meeting & File Repository |  | Document Storage & Meeting Collaboration |  | Document Repository & Collaboration Tools |  | Zoho Meeting & Zoho Mail Alias Setup | Connect Zoho Meeting for 1-click project conferencing and configure project email aliases for direct email-to-task routing. | 0.50 | Integration | Low | 0.40 | 0.80 | Meeting launch button and inbound project email alias functional. | Zoho Meeting / Mail licenses available. | No | No | Document Storage & Meeting Collaboration › File Uploads, Previews & Version History | Requires
Basic | Zoho Projects | Basic Issue / Bug Tracking | Centralized defect capture, severity matrices, and standard issue resolution lifecycles. | Issue & Bug Tracking Engine | Systematic issue logging and resolution workflows linked to project deliverables. | Issue Tracking & Resolution Workflow | Set up bug categories, severity levels, and resolution states. | Issue Logging & Classification Setup | Activate Issue Tracker module, configure custom bug severity levels, classifications, and link issues directly to affected tasks. | 1.00 | Configuration | Low | 0.80 | 1.20 | Issue logging interface active with custom severity tags. | Issue classification rules agreed. | Yes | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Basic | Zoho Projects | Basic Issue / Bug Tracking |  | Issue & Bug Tracking Engine |  | Issue Tracking & Resolution Workflow |  | Standard Issue Lifecycle States & Workflow | Configure issue resolution states (Open, In Investigation, In Fix, Verified, Closed) with mandatory technician assignment. | 1.00 | Configuration | Low | 0.80 | 1.20 | Governed issue lifecycle workflow active. | Issue workflow states confirmed. | No | No | Issue & Bug Tracking Engine › Issue Logging & Classification Setup | Requires
Basic | Zoho Projects | Team Training, Walkthrough & SOPs | Role-based end-user training workshops, hands-on user walkthroughs, and standard operating procedure quick guides. | User Enablement & Operational Handover | Structured training sprints ensuring rapid, high-confidence team adoption. | Training Academy & Delivery Handover | Conduct PM training, team work logging sessions, and deliver SOP documentation. | Project Manager Hands-On Training | Conduct live interactive training for Project Managers on project creation, Gantt scheduling, task assignment, and timesheets. | 1.50 | Training | Medium | 1.20 | 2.00 | Completed training session for PMs with recorded walkthrough video. | Basic configuration completed. | Yes | No | Timesheet Configuration & Work Logging › Standard Timesheet Approval Flow | Requires
Basic | Zoho Projects | Team Training, Walkthrough & SOPs |  | User Enablement & Operational Handover |  | Training Academy & Delivery Handover |  | Team Member Task & Time Tracking Training | Deliver hands-on training for team members covering task updates, checklist completion, document uploads, and stopwatch work logging. | 1.50 | Training | Low | 1.20 | 2.00 | Completed team member training session with attendance log. | PM training completed. | Yes | No | User Enablement & Operational Handover › Project Manager Hands-On Training | Requires
Basic | Zoho Projects | Team Training, Walkthrough & SOPs |  | User Enablement & Operational Handover |  | Training Academy & Delivery Handover |  | Standard Operating Procedure (SOP) Quick Guide | Provide a tailored, concise PDF quick-reference SOP guide covering daily task tracking, timesheets, and support issue workflows. | 1.00 | Documentation | Low | 0.80 | 1.20 | Branded PDF SOP manual delivered to client leadership. | Workflows finalized. | No | No | User Enablement & Operational Handover › Team Member Task & Time Tracking Training | Requires
Professional | Zoho Projects | Multi-Department Workspace & Custom Domain | Enterprise multi-department portfolio structures, custom branded portal domains, and multi-regional holiday calendars. | Multi-Department Workspace Architecture | Segmented project workspaces across business units with dedicated custom domains. | Departmental Portfolio & Domain Branding | Structure cross-departmental portfolios, custom domain mapping, and regional calendars. | Multi-Department Portfolio Structure | Structure segmented project workspaces, tags, and access boundaries across discrete business units or branch operations. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Multi-departmental portfolio structure active with segregated views. | Departmental organization chart approved. | Yes | No | Portfolio Taxonomy & Categorization › Project Groups & Master Tag Library | Requires
Professional | Zoho Projects | Multi-Department Workspace & Custom Domain |  | Multi-Department Workspace Architecture |  | Departmental Portfolio & Domain Branding |  | Custom Domain Mapping & Portal URL Branding | Configure custom domain mapping (e.g., projects.company.com) with SSL certificate provisioning and white-label URL access. | 1.50 | Security | Medium | 1.00 | 2.00 | Active branded portal URL with verified SSL certificate. | DNS CNAME record access provided by client IT. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Professional | Zoho Projects | Multi-Department Workspace & Custom Domain |  | Multi-Department Workspace Architecture |  | Departmental Portfolio & Domain Branding |  | Multi-Regional Holiday Calendars | Set up multiple regional and international holiday calendars linked to specific team members to automate scheduling across distributed offices. | 1.00 | Configuration | Low | 0.80 | 1.50 | Multi-regional holiday calendars mapped to user groups. | Regional holiday schedules provided. | Yes | No | Portal & Global Configuration Setup › Work Calendar, Timezone & Operating Hours | Requires
Professional | Zoho Projects | Granular Roles, Profiles & Field Security | Granular permission sets, external client user permissions, and confidential field masking. | Granular Profile & Permission Matrix | Fine-grained security governing module access, rate visibility, and project confidentiality. | Access Control & Field Security | Build custom profile matrices, external client roles, and field masking. | Granular Custom Role & Designation Matrices | Build tailored permission profiles (PM, Lead Architect, Financial Controller, Contractor) with granular create/edit/delete limits. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Detailed custom profile matrix active with role assignments. | Role permissions policy approved. | Yes | No | User Administration & Role Governance › User Profiles & Standard Role Matrix | Requires
Professional | Zoho Projects | Granular Roles, Profiles & Field Security |  | Granular Profile & Permission Matrix |  | Access Control & Field Security |  | Client User Setup & External Permissions | Configure external Client User profiles with restricted view permissions limited strictly to designated deliverables and milestones. | 1.50 | Configuration | Medium | 1.00 | 2.00 | Client external user profile configured and tested. | Client visibility requirements defined. | Yes | No | Granular Profile & Permission Matrix › Granular Custom Role & Designation Matrices | Requires
Professional | Zoho Projects | Granular Roles, Profiles & Field Security |  | Granular Profile & Permission Matrix |  | Access Control & Field Security |  | Confidential Project Security & Field Masking | Enforce field-level security and confidential project flags to restrict budget, billing rates, and contractual fields from non-finance staff. | 1.00 | Security | Medium | 0.80 | 1.50 | Field masking verified across restricted employee roles. | Confidential data fields identified. | No | No | Granular Profile & Permission Matrix › Client User Setup & External Permissions | Requires
Professional | Zoho Projects | Multi-Template Library & Dependency Logic | Extended template repository (up to 20+ templates), advanced predecessor logic, and automatic schedule shifting. | Advanced Template & Scheduling Engine | Complex dependency modeling and dynamic schedule shifting across diverse project typologies. | Template Library & Dependency Architecture | Build extended template gallery and all four dependency logic models. | Extended Project Template Library (Up to 20+) | Develop and calibrate up to 20 comprehensive project delivery templates across diverse client engagement models. | 2.50 | Configuration | Medium | 2.00 | 3.50 | Complete library of up to 20 reusable project templates. | Standardized WBS workflows across departments. | Yes | No | Project Template & Delivery Standardization › Master Project Template Creation (Up to 5) | Requires
Professional | Zoho Projects | Multi-Template Library & Dependency Logic |  | Advanced Template & Scheduling Engine |  | Template Library & Dependency Architecture |  | Advanced Dependency Architecture (FS, SS, FF, SF) | Configure all four dependency logic models (Finish-to-Start, Start-to-Start, Finish-to-Finish, Start-to-Finish) with lead and lag time settings. | 1.50 | Configuration | Medium | 1.00 | 2.00 | 4-tier dependency logic validated on complex template schedules. | Dependency logic mapped. | No | No | Advanced Template & Scheduling Engine › Extended Project Template Library (Up to 20+) | Requires
Professional | Zoho Projects | Multi-Template Library & Dependency Logic |  | Advanced Template & Scheduling Engine |  | Template Library & Dependency Architecture |  | Strict Project Scheduling & Auto-Rescheduling | Implement strict scheduling constraints and automated rescheduling rules when deliverable timelines or predecessor tasks shift. | 1.50 | Configuration | Medium | 1.00 | 2.00 | Strict auto-rescheduling rules operational. | Scheduling rules agreed. | No | No | Advanced Template & Scheduling Engine › Advanced Dependency Architecture (FS, SS, FF, SF) | Requires
Professional | Zoho Projects | Task Breakdown Structure (WBS), Views & Dynamic Layouts | Custom project and task fields, dynamic layout visibility rules, custom status workflows, and embedded web tabs. | Custom Data Architecture & Dynamic Layouts | Tailor data structures and conditional visibility across project layouts. | Custom Fields & Dynamic Layout Rules | Configure custom fields, visibility rules, and web tabs. | Custom Project & Task Field Architecture | Build custom fields (currency, formula, user lookup, dropdown, date) across projects, tasks, and milestone layouts. | 2.50 | Customization | Medium | 2.00 | 3.00 | Custom field data architecture active across modules. | Custom field data dictionary approved. | Yes | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Professional | Zoho Projects | Task Breakdown Structure (WBS), Views & Dynamic Layouts |  | Custom Data Architecture & Dynamic Layouts |  | Custom Fields & Dynamic Layout Rules |  | Dynamic Layout Rules & Conditional Visibility | Set up conditional field rules showing or hiding task parameters dynamically based on project type, priority, or stage selection. | 2.00 | Customization | Medium | 1.50 | 2.50 | Dynamic layout rules active and verified. | Field conditional logic mapped. | No | No | Custom Data Architecture & Dynamic Layouts › Custom Project & Task Field Architecture | Requires
Professional | Zoho Projects | Task Breakdown Structure (WBS), Views & Dynamic Layouts |  | Custom Data Architecture & Dynamic Layouts |  | Custom Fields & Dynamic Layout Rules |  | Custom Status Workflows & Custom Web Tabs | Design custom status workflows per project category and embed custom web tabs linking external portals or live dashboards directly in projects. | 1.50 | Customization | Low | 1.00 | 2.00 | Custom status flows and embedded web tabs functional. | External web tab URLs confirmed. | Yes | No | Custom Data Architecture & Dynamic Layouts › Dynamic Layout Rules & Conditional Visibility | Requires
Professional | Zoho Projects | Milestone & Task Blueprints (Process Governance) | Visual state machine governance, mandatory checklist validations, digital sign-offs, and automated stage actions. | Visual State Machine Blueprints | Enforce operational compliance and prevent unauthorized task progression through rigid stage-gates. | Blueprint Design & Gatekeeping | Design visual state machines, sign-offs, and automated transitions. | Task Status Blueprint Design | Design visual state machine Blueprints defining allowed status transitions and authorized role transitions for project tasks. | 3.00 | Customization | High | 2.50 | 4.00 | Active Task Status Blueprint controlling lifecycle states. | Task lifecycle state transitions documented. | Yes | No | Custom Data Architecture & Dynamic Layouts › Custom Status Workflows & Custom Web Tabs | Requires
Professional | Zoho Projects | Milestone & Task Blueprints (Process Governance) |  | Visual State Machine Blueprints |  | Blueprint Design & Gatekeeping |  | Milestone Gatekeeping & Deliverable Sign-Offs | Configure mandatory transition criteria requiring document attachments, sign-off notes, and mandatory checklist completion before stage advancement. | 2.00 | Customization | Medium | 1.50 | 2.50 | Mandatory gatekeeping rules preventing premature task closure. | Mandatory deliverable checklists agreed. | No | No | Visual State Machine Blueprints › Task Status Blueprint Design | Requires
Professional | Zoho Projects | Milestone & Task Blueprints (Process Governance) |  | Visual State Machine Blueprints |  | Blueprint Design & Gatekeeping |  | Automated Blueprint Actions, Macros & Alerts | Attach automated field updates, email alerts, and webhook triggers that execute dynamically during Blueprint stage transitions. | 2.00 | Customization | Medium | 1.50 | 2.50 | Automated transition triggers functional on status changes. | Notification recipients confirmed. | No | No | Visual State Machine Blueprints › Milestone Gatekeeping & Deliverable Sign-Offs | Requires
Professional | Zoho Projects | Interactive Gantt Scheduling & Project Baselines | Critical Path Method (CPM) calculation, multi-version baseline comparisons, and portfolio Gantt views. | Critical Path (CPM) & Baseline Variance | Schedule risk optimization, zero-slack bottlenecks, and contractual baseline variance tracking. | CPM Scheduling & Baseline Management | Set up CPM calculation, baselines, and multi-project Gantt. | Advanced Gantt Configuration & Critical Path | Configure dynamic Critical Path identification, automatic schedule compression options, and zero-slack task highlights. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Dynamic Critical Path highlighted across project schedules. | Task dependencies configured. | No | No | Advanced Template & Scheduling Engine › Advanced Dependency Architecture (FS, SS, FF, SF) | Requires
Professional | Zoho Projects | Interactive Gantt Scheduling & Project Baselines |  | Critical Path (CPM) & Baseline Variance |  | CPM Scheduling & Baseline Management |  | Project Baseline Tracking & Variance Analysis | Lock initial project schedule baseline and configure visual variance comparison bars tracking deviations between planned vs actual dates. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Locked baseline version with visual Gantt variance overlays. | Baseline schedule approved. | Yes | No | Critical Path (CPM) & Baseline Variance › Advanced Gantt Configuration & Critical Path | Requires
Professional | Zoho Projects | Interactive Gantt Scheduling & Project Baselines |  | Critical Path (CPM) & Baseline Variance |  | CPM Scheduling & Baseline Management |  | Multi-Project Portfolio Gantt View | Configure cross-project Chronological Gantt overview allowing management to track overlapping timelines across the entire active portfolio. | 1.50 | Configuration | Low | 1.00 | 2.00 | Cross-project portfolio Gantt dashboard operational. | Multiple active projects populated. | No | No | Critical Path (CPM) & Baseline Variance › Project Baseline Tracking & Variance Analysis | Requires
Professional | Zoho Projects | Resource Capacity Planning & Workload Balancing | Resource utilization heatmaps, daily/weekly capacity allocation limits, burnout detection, and Zoho People leave sync. | Resource Capacity & Utilization Engine | Real-time visibility into staff availability and cross-project workload balancing. | Resource Leveling & People Sync | Configure utilization heatmaps, workload balancing, and leave calendar sync. | Resource Allocation & Heatmap Setup | Configure color-coded Resource Utilization Chart showing daily and weekly allocation hours against predefined working limits. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Active Resource Utilization Heatmap showing real-time staff loads. | Staff working hours and role allocation agreed. | Yes | No | Portal & Global Configuration Setup › Work Calendar, Timezone & Operating Hours | Requires
Professional | Zoho Projects | Resource Capacity Planning & Workload Balancing |  | Resource Capacity & Utilization Engine |  | Resource Leveling & People Sync |  | Workload Leveling & Over-Allocation Mitigation | Establish resource allocation rules and visual warning thresholds flagging team members scheduled above 100% capacity. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Over-allocation alerts active with drag-and-drop task re-leveling. | Capacity thresholds confirmed. | No | No | Resource Capacity & Utilization Engine › Resource Allocation & Heatmap Setup | Requires
Professional | Zoho Projects | Resource Capacity Planning & Workload Balancing |  | Resource Capacity & Utilization Engine |  | Resource Leveling & People Sync |  | Zoho People Leave Integration & Shift Sync | Connect Zoho People to dynamically ingest employee approved leave, holidays, and working shifts directly into project scheduling calendars. | 1.50 | Integration | Medium | 1.00 | 2.00 | Bi-directional leave sync active between Zoho People and Projects. | Zoho People organization access available. | Yes | No | Resource Capacity & Utilization Engine › Workload Leveling & Over-Allocation Mitigation | Requires
Professional | Zoho Projects | Advanced Timesheets, Multi-Tier Billing & Approvals | Staff/Role/Project hourly billing rates, mobile tracking, multi-tier approval chains, and payroll lock periods. | Multi-Tier Billing Rates & Approvals | Commercial rate card modeling and multi-stage financial approval chains. | Billing Rates & Governance Approval | Set up rate cards, mobile timers, and lockdown periods. | Multi-Tier Billing Rates Architecture | Configure Staff-Based, Role-Based, and Project-Based hourly billing rates for accurate client invoicing and costing. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Configured rate cards active across all billing roles. | Contractual billing rate schedule provided. | Yes | No | Time Tracking & Timesheet Logging › Daily & Weekly Timesheet Logging | Requires
Professional | Zoho Projects | Advanced Timesheets, Multi-Tier Billing & Approvals |  | Multi-Tier Billing Rates & Approvals |  | Billing Rates & Governance Approval |  | Live Stopwatch Timer & Mobile Tracking | Configure in-app live multi-timer stopwatch and mobile time tracking with automated background work logging. | 1.50 | Configuration | Low | 1.00 | 2.00 | Mobile time tracking verified with background work sync. | Mobile app access enabled. | No | No | Multi-Tier Billing Rates & Approvals › Multi-Tier Billing Rates Architecture | Requires
Professional | Zoho Projects | Advanced Timesheets, Multi-Tier Billing & Approvals |  | Multi-Tier Billing Rates & Approvals |  | Billing Rates & Governance Approval |  | Multi-Tier Timesheet Approval & Lock Periods | Establish multi-stage approval workflows (PM -> Finance Head) with automated timesheet lockdown at payroll cutoff. | 2.50 | Configuration | Medium | 2.00 | 3.00 | Automated payroll lock periods active preventing past edits. | Payroll cutoff cycle confirmed. | Yes | No | Multi-Tier Billing Rates & Approvals › Live Stopwatch Timer & Mobile Tracking | Requires
Professional | Zoho Projects | Issue / Bug SLA Management & Business Rules | Custom bug tracking layouts, SLA targets, automated business assignment rules, and escalation hierarchies. | Issue SLA & Business Automation Rules | Enforce strict contractual response and resolution SLAs with automated multi-tier escalations. | SLA Governance & Issue Automation | Set up custom bug layouts, SLA targets, and escalation triggers. | Custom Issue Layouts, Email-to-Issue & Views | Build custom bug tracking layouts, custom severity matrices, email-to-issue alias, and issue-to-task linking. | 2.00 | Customization | Medium | 1.50 | 2.50 | Custom issue tracking layout with inbound email parser. | Issue fields dictionary approved. | Yes | No | Issue & Bug Tracking Engine › Issue Logging & Classification Setup | Requires
Professional | Zoho Projects | Issue / Bug SLA Management & Business Rules |  | Issue SLA & Business Automation Rules |  | SLA Governance & Issue Automation |  | SLA Management & Business Rules Auto-Assign | Configure formal SLAs (First Response & Resolution) and automated business rules for auto-assignment and field updates. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Active SLA policies with automatic technician assignment. | Contractual SLA targets confirmed. | Yes | No | Issue SLA & Business Automation Rules › Custom Issue Layouts, Email-to-Issue & Views | Requires
Professional | Zoho Projects | Issue / Bug SLA Management & Business Rules |  | Issue SLA & Business Automation Rules |  | SLA Governance & Issue Automation |  | Multi-Level Escalation Automation Rules | Automate multi-tier escalation triggers routing SLA-breaching issues to senior leadership via high-priority alerts. | 1.50 | Configuration | Low | 1.00 | 2.00 | Multi-level escalation rules active on SLA breach. | Escalation recipients documented. | No | No | Issue SLA & Business Automation Rules › SLA Management & Business Rules Auto-Assign | Requires
Professional | Zoho Projects | Ecosystem Integrations: Zoho Books, CRM & Office | Direct Zoho Books timesheet-to-invoice sync, Zoho CRM Deal Won auto-provisioning, and MS 365 / Google Workspace sync. | Ecosystem Closed-Loop Integrations | Bridge sales pipeline handoff, back-office billing, and team collaboration into an automated pipeline. | Books, CRM & Office Cloud Interconnect | Connect Books timesheet invoicing, CRM deal templates, and Office suites. | Direct Zoho Books Timesheet-to-Invoice Sync | Configure bi-directional sync linking Zoho Projects with Zoho Books/Invoice for one-click invoice generation from approved hours. | 2.50 | Integration | High | 2.00 | 3.50 | 1-click client invoice generation operational from approved timesheets. | Zoho Books organization access and chart of accounts confirmed. | Yes | No | Multi-Tier Billing Rates & Approvals › Multi-Tier Timesheet Approval & Lock Periods | Requires
Professional | Zoho Projects | Ecosystem Integrations: Zoho Books, CRM & Office |  | Ecosystem Closed-Loop Integrations |  | Books, CRM & Office Cloud Interconnect |  | Zoho CRM Deal-to-Project Auto-Creation | Auto-instantiate project templates upon Deal Won in Zoho CRM, syncing client details, scope deliverables, and target dates. | 2.00 | Integration | Medium | 1.50 | 2.50 | Automated project provisioning verified upon CRM Deal Won trigger. | Zoho CRM deal stages and field mapping agreed. | Yes | No | Project Template & Delivery Standardization › Master Project Template Creation (Up to 5) | Requires
Professional | Zoho Projects | Ecosystem Integrations: Zoho Books, CRM & Office |  | Ecosystem Closed-Loop Integrations |  | Books, CRM & Office Cloud Interconnect |  | Google Workspace & Microsoft 365 Integration | Connect Google Drive/Calendar and Microsoft Teams/Outlook/OneDrive/SharePoint with CSV & MS Project (.mpp) migration. | 2.50 | Integration | Medium | 2.00 | 3.00 | MS 365 / Google Workspace sync active with document repository. | Cloud tenant admin credentials available. | Yes | No | Document Storage & Meeting Collaboration › Project Folder & Document Hierarchy | Requires
Professional | Zoho Projects | Departmental Training, Simulation & 30-Day Hypercare | Departmental role-based training workshops, 25+ real-data UAT scenario simulations, and dedicated 30-day post go-live hypercare. | Professional Change Management & Hypercare | Rigorous UAT validation and dedicated consultant support ensuring zero-defect go-live. | Training Sprints, UAT & Post-Go-Live Care | Deliver training academies, simulate UAT, and provide 30-day hypercare. | Departmental Training Sprints | Deliver specialized training workshops for Project Managers, Resource Planners, and Finance/Billing administrators. | 2.50 | Training | Medium | 2.00 | 3.00 | Completed training sprints for PMs, resource planners, and billing team. | All professional configuration modules validated. | Yes | No | Ecosystem Closed-Loop Integrations › Direct Zoho Books Timesheet-to-Invoice Sync | Requires
Professional | Zoho Projects | Departmental Training, Simulation & 30-Day Hypercare |  | Professional Change Management & Hypercare |  | Training Sprints, UAT & Post-Go-Live Care |  | User Acceptance Testing (UAT) Simulation | Simulate 25+ real client delivery scenarios: scope changes, baseline shifts, contractor timesheets, and invoice sync. | 2.00 | Validation | Medium | 1.50 | 2.50 | Formal signed UAT sign-off document with zero open defects. | UAT test cases and client test team available. | Yes | No | Professional Change Management & Hypercare › Departmental Training Sprints | Requires
Professional | Zoho Projects | Departmental Training, Simulation & 30-Day Hypercare |  | Professional Change Management & Hypercare |  | Training Sprints, UAT & Post-Go-Live Care |  | 30-Day Post Go-Live Hypercare | Dedicated consultant on-call support during first monthly project closing, client billing run, and resource reviews. | 1.50 | Support | Low | 1.00 | 2.00 | Completed 30-day hypercare period with monthly project closing report. | Production cutover executed. | Yes | No | Professional Change Management & Hypercare › User Acceptance Testing (UAT) Simulation | Requires
Elite | Zoho Projects | Critical Path Method (CPM), Schedule Risk & Baseline Engine | Enterprise CPM optimization, zero-slack bottlenecks, unlimited baseline comparison engine, and automated schedule risk alerts. | Enterprise CPM & Baseline Governance | Mathematical critical path optimization and multi-version baseline comparison across complex programs. | CPM Optimization & Baseline Versioning | Configure CPM calculation, baseline versions, and buffer management. | Critical Path Method (CPM) Optimization | Identify true critical path deliverables, zero-slack tasks, and automated schedule compression options. | 3.00 | Configuration | High | 2.50 | 4.00 | Dynamic CPM calculation active highlighting zero-slack deliverable paths. | Complex WBS dependencies established. | No | No | Critical Path (CPM) & Baseline Variance › Advanced Gantt Configuration & Critical Path | Requires
Elite | Zoho Projects | Critical Path Method (CPM), Schedule Risk & Baseline Engine |  | Enterprise CPM & Baseline Governance |  | CPM Optimization & Baseline Versioning |  | Multi-Version Baseline Comparison Engine | Maintain unlimited baseline versions (Original Contract, Approved Scope Change, Revised Schedule) with variance tracking. | 3.00 | Configuration | Medium | 2.50 | 3.50 | Multi-version baseline comparison active with visual variance overlays. | Baseline versioning criteria confirmed. | Yes | No | Enterprise CPM & Baseline Governance › Critical Path Method (CPM) Optimization | Requires
Elite | Zoho Projects | Critical Path Method (CPM), Schedule Risk & Baseline Engine |  | Enterprise CPM & Baseline Governance |  | CPM Optimization & Baseline Versioning |  | Schedule Variance & Buffer Management | Automate slack time tracking, schedule performance index warnings, and delay alerts for program managers. | 2.50 | Configuration | Medium | 2.00 | 3.00 | Automated slack buffer threshold alerts operational. | Schedule risk thresholds defined. | No | No | Enterprise CPM & Baseline Governance › Multi-Version Baseline Comparison Engine | Requires
Elite | Zoho Projects | Multi-Project Resource Forecasting & Capacity Balancing | Cross-project capacity forecasting 3 to 6 months in advance, multi-project resource balancing, and labor margin yield analytics. | Enterprise Resource Forecasting & Margin Analytics | Long-term capacity forecasting and real-time labor yield margin tracking. | Resource Capacity Forecasting & Yield Optimization | Build 3-6 month forecasting views, balancing rules, and labor margin yield analytics. | Multi-Project Resource Capacity Forecasting | Forecast team and department capacity requirements 3 to 6 months in advance based on active and pipeline project commitments. | 3.50 | Configuration | High | 3.00 | 4.50 | Forward-looking 6-month capacity forecast model operational. | Pipeline resource demand profiles agreed. | Yes | No | Resource Capacity & Utilization Engine › Resource Allocation & Heatmap Setup | Requires
Elite | Zoho Projects | Multi-Project Resource Forecasting & Capacity Balancing |  | Enterprise Resource Forecasting & Margin Analytics |  | Resource Capacity Forecasting & Yield Optimization |  | Multi-Project Resource Balancing & Allocation Rules | Configure cross-project resource utilization views and daily/weekly capacity allocation limits to eliminate multi-project over-commitment. | 3.00 | Configuration | Medium | 2.50 | 3.50 | Multi-project balancing rules active preventing dual-booking. | Cross-project allocation priorities set. | No | No | Enterprise Resource Forecasting & Margin Analytics › Multi-Project Resource Capacity Forecasting | Requires
Elite | Zoho Projects | Multi-Project Resource Forecasting & Capacity Balancing |  | Enterprise Resource Forecasting & Margin Analytics |  | Resource Capacity Forecasting & Yield Optimization |  | Resource Cost vs. Billing Margin Yield Analytics | Compare staff cost rates against client billing rates to analyze real-time gross margin and labor yield per team member and department. | 3.00 | Configuration | High | 2.50 | 3.50 | Labor margin yield analytics view operational. | Internal cost rate cards and external billing rates provided. | Yes | No | Enterprise Resource Forecasting & Margin Analytics › Multi-Project Resource Balancing & Allocation Rules | Requires
Elite | Zoho Projects | Enterprise Project Budgeting & EVM Financial Flow | Hierarchical amount/hour budgets, live cost burn tracking, automated threshold escalations, hard-stop budget freezes, and Earned Value Management (EVM). | Enterprise Project Budgeting & EVM Flow | Closed-loop financial governance protecting project gross margins against budget overruns. | Budget Architecture & EVM Controls | Configure hierarchical budgets, real-time cost burn, Deluge hard freeze, and EVM formulas. | Multi-Tier Budget Architecture & Baseline Allocation | Setup hierarchical project-level, milestone-level, and task-level budgeting in amount and hours with baseline cost cards and profit margin models. | 3.50 | Configuration | High | 3.00 | 4.50 | Hierarchical multi-tier budget structure active across active projects. | Project budget allocation models approved. | Yes | No | Multi-Tier Billing Rates & Approvals › Multi-Tier Billing Rates Architecture | Requires
Elite | Zoho Projects | Enterprise Project Budgeting & EVM Financial Flow |  | Enterprise Project Budgeting & EVM Flow |  | Budget Architecture & EVM Controls |  | Real-Time Cost Burn, Expense Ingestion & Margin Tracking | Automate live ingestion of staff timesheet costs and categorized project expenses (direct, subcontractor, overhead) to compute live gross margin burn. | 3.50 | Configuration | High | 3.00 | 4.50 | Live gross margin burn engine calculating actual cost in real time. | Direct and overhead expense categories mapped. | Yes | No | Enterprise Project Budgeting & EVM Flow › Multi-Tier Budget Architecture & Baseline Allocation | Requires
Elite | Zoho Projects | Enterprise Project Budgeting & EVM Financial Flow |  | Enterprise Project Budgeting & EVM Flow |  | Budget Architecture & EVM Controls |  | Automated Budget Threshold Escalations & Hard-Stop Freeze | Configure automated multi-tier alert triggers (50%, 80%, 100%) and Deluge/Blueprint hard-stop validation locks halting unapproved work logs upon budget breach. | 3.00 | Customization | High | 2.50 | 4.00 | Deluge hard-stop freeze operational, blocking work logging upon 100% budget breach. | Budget breach escalation protocol approved. | Yes | Yes | Enterprise Project Budgeting & EVM Flow › Real-Time Cost Burn, Expense Ingestion & Margin Tracking | Requires
Elite | Zoho Projects | Enterprise Project Budgeting & EVM Financial Flow |  | Enterprise Project Budgeting & EVM Flow |  | Budget Architecture & EVM Controls |  | Earned Value Management (EVM) & Revenue Realization Flow | Configure Planned Value (PV), Earned Value (EV), Actual Cost (AC), CPI, SPI, EAC, and link milestone deliverables to revenue realization in Zoho Books. | 3.00 | Configuration | High | 2.50 | 4.00 | EVM metric calculations (CPI/SPI/EAC) live with Books revenue realization sync. | Financial recognition rules approved. | Yes | No | Enterprise Project Budgeting & EVM Flow › Automated Budget Threshold Escalations & Hard-Stop Freeze | Requires
Elite | Zoho Projects | Custom Modules Architecture & Enterprise Issue Governance | Dedicated custom data entities (Change Requests, Submittals, RFIs), multi-channel bug ingestion, and strict contractual SLA penalty tracking. | Custom Modules & Issue SLA Governance | Extend data architecture for non-standard governance entities with contractual SLA penalties. | Custom Modules & Contractual SLA Management | Build Change Request custom modules, webhook ingestion, and penalty SLA rules. | Custom Modules Setup (Change Requests & Non-Standard Entities) | Build dedicated custom data entities within Zoho Projects (e.g., Change Requests, Submittals, RFI) with custom layouts and relational links. | 3.00 | Customization | High | 2.50 | 4.00 | Custom modules active with relational links to projects and milestones. | Custom entity data specifications provided. | Yes | No | Custom Data Architecture & Dynamic Layouts › Custom Project & Task Field Architecture | Requires
Elite | Zoho Projects | Custom Modules Architecture & Enterprise Issue Governance |  | Custom Modules & Issue SLA Governance |  | Custom Modules & Contractual SLA Management |  | Multi-Channel Issue / Bug Ingestion & Webhooks | Capture issues and defects via web forms, customer portals, email-to-issue parsers, and external QA webhook pipelines. | 3.00 | Integration | Medium | 2.50 | 3.50 | Inbound QA webhook endpoints and multi-channel intake pipelines verified. | External QA systems identified. | Yes | Yes | Custom Modules & Issue SLA Governance › Custom Modules Setup (Change Requests & Non-Standard Entities) | Requires
Elite | Zoho Projects | Custom Modules Architecture & Enterprise Issue Governance |  | Custom Modules & Issue SLA Governance |  | Custom Modules & Contractual SLA Management |  | Multi-Tier Escalation Hierarchies & Penalty SLA Tracking | Automate strict contractual SLA breach notifications to executives and client representatives with penalty calculation flags. | 2.50 | Configuration | Medium | 2.00 | 3.00 | Contractual SLA breach penalty tracking and C-suite alert triggers operational. | Contractual SLA penalty terms confirmed. | Yes | No | Custom Modules & Issue SLA Governance › Multi-Channel Issue / Bug Ingestion & Webhooks | Requires
Elite | Zoho Projects | Multi-Stakeholder Client & Subcontractor Sandboxed Portals | Segmented external portal environments, subcontractor task work logging, and formal change order digital approval workflows. | Multi-Stakeholder Sandboxed Portals | Secure, segmented portal architecture for external clients, subcontractors, and vendors. | External Portal Architecture & Sandboxing | Configure client and vendor sandboxes with digital change order sign-offs. | Multi-Tier External Portal Architecture | Configure segmented, secure portal environments for enterprise clients, subcontractors, and freelance specialists. | 3.00 | Security | High | 2.50 | 4.00 | Multi-stakeholder external portal environments configured with restricted security. | External access policies approved. | Yes | No | Granular Profile & Permission Matrix › Client User Setup & External Permissions | Requires
Elite | Zoho Projects | Multi-Stakeholder Client & Subcontractor Sandboxed Portals |  | Multi-Stakeholder Sandboxed Portals |  | External Portal Architecture & Sandboxing |  | Subcontractor Task Assignment & Work Logging | Enable external contractors to log task progress and billable hours within restricted project sandboxes without visibility to full scope. | 2.50 | Configuration | Medium | 2.00 | 3.00 | Subcontractor sandbox access operational with blind internal commercial data. | Contractor work scope defined. | No | No | Multi-Stakeholder Sandboxed Portals › Multi-Tier External Portal Architecture | Requires
Elite | Zoho Projects | Multi-Stakeholder Client & Subcontractor Sandboxed Portals |  | Multi-Stakeholder Sandboxed Portals |  | External Portal Architecture & Sandboxing |  | Client Deliverable Sign-Off & Change Order Approval | Build formal change order request workflows requiring client digital approval before scope, budget, or timeline adjustments. | 2.50 | Customization | Medium | 2.00 | 3.00 | Digital change order sign-off workflow active in client portal. | Client approval authority matrix provided. | Yes | No | Multi-Stakeholder Sandboxed Portals › Subcontractor Task Assignment & Work Logging | Requires
Elite | Zoho Projects | Client Collaboration Portal, Pages (Wiki) & Forums | Branded client self-service portal, deliverable milestone approval workflows, and interactive project documentation Wikis. | Client Collaboration & Knowledge Wikis | Transparent client engagement and standardized interactive project documentation. | Client Self-Service & Wiki Governance | Set up client self-service, milestone sign-offs, and project Wikis. | Branded Client Self-Service Portal | Configure secure client portal access with restricted visibility limited exclusively to designated tasks and milestones. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Branded client self-service portal active with custom branding. | Client branding assets provided. | Yes | No | Multi-Stakeholder Sandboxed Portals › Multi-Tier External Portal Architecture | Requires
Elite | Zoho Projects | Client Collaboration Portal, Pages (Wiki) & Forums |  | Client Collaboration & Knowledge Wikis |  | Client Self-Service & Wiki Governance |  | Client Deliverable Approval Workflows | Enable external client stakeholders to review completed deliverables, approve milestones, or request revisions directly. | 1.50 | Configuration | Medium | 1.00 | 2.00 | Client review and milestone approval state active. | Deliverable acceptance criteria confirmed. | Yes | No | Client Collaboration & Knowledge Wikis › Branded Client Self-Service Portal | Requires
Elite | Zoho Projects | Client Collaboration Portal, Pages (Wiki) & Forums |  | Client Collaboration & Knowledge Wikis |  | Client Self-Service & Wiki Governance |  | Interactive Forums, Pages (Wiki) & Docs | Setup project discussion forums, announcement boards, and interactive Wiki pages for standardized project documentation. | 1.50 | Configuration | Low | 1.00 | 2.00 | Project Wiki templates and discussion forums active. | Documentation templates provided. | No | No | Client Collaboration & Knowledge Wikis › Client Deliverable Approval Workflows | Requires
Elite | Zoho Projects | Zoho Ecosystem Deep Interconnect (Desk, People, Sprints) | Bi-directional Zoho Desk ticket-to-task sync, Zoho People leave/shifts sync, and Zoho Sprints hybrid agile synchronization. | Zoho Ecosystem Deep Interconnect | Unified cross-application handoffs connecting customer support, agile sprints, and HR calendars. | Desk, People & Sprints Tri-Directional Sync | Configure Desk ticket sync, People leave/shifts, and Sprints integration. | Zoho Desk Ticket-to-Task / Bug Interconnect | Bi-directional sync converting customer support tickets into project tasks or bugs with live status reflection. | 3.50 | Integration | High | 3.00 | 4.50 | Bi-directional ticket-to-task sync operational with live status reflection. | Zoho Desk department access available. | Yes | No | Issue & Bug Tracking Engine › Issue Logging & Classification Setup | Requires
Elite | Zoho Projects | Zoho Ecosystem Deep Interconnect (Desk, People, Sprints) |  | Zoho Ecosystem Deep Interconnect |  | Desk, People & Sprints Tri-Directional Sync |  | Zoho People Employee Leaves & Resource Calendar Sync | Live two-way sync of employee leave approvals, shifts, and public holidays into project timelines. | 3.50 | Integration | Medium | 3.00 | 4.00 | Two-way employee leave and shift sync active across all projects. | Zoho People integration permissions enabled. | Yes | No | Resource Capacity & Utilization Engine › Zoho People Leave Integration & Shift Sync | Requires
Elite | Zoho Projects | Zoho Ecosystem Deep Interconnect (Desk, People, Sprints) |  | Zoho Ecosystem Deep Interconnect |  | Desk, People & Sprints Tri-Directional Sync |  | Zoho Sprints & Cliq Interactive Channels | Configure hybrid agile sprint syncing with Zoho Sprints and auto-create dedicated Cliq project channels and standups. | 3.00 | Integration | Medium | 2.50 | 3.50 | Hybrid agile sprint sync and automated Cliq project bot operational. | Zoho Sprints & Cliq access available. | Yes | No | Zoho Ecosystem Deep Interconnect › Zoho People Employee Leaves & Resource Calendar Sync | Requires
Elite | Zoho Projects | Custom Deluge Scripting & Enterprise Workflow Functions | Complex serverless Deluge functions, automated parent task completion, dynamic deadline recalculation, and notification bots. | Serverless Deluge Automation Engine | Custom business logic development executing dynamic project computations and portfolio notifications. | Deluge Scripts & Advanced Business Logic | Develop custom rollups, cross-module validation, and executive bots. | Complex Deluge Business Logic Development | Develop custom Deluge functions for automated parent task completion, dynamic deadline recalculation, and custom rollups. | 5.50 | Customization | High | 4.50 | 7.00 | Custom Deluge functions deployed and executing upon task update triggers. | Custom calculation logic signed off. | Yes | Yes | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Elite | Zoho Projects | Custom Deluge Scripting & Enterprise Workflow Functions |  | Serverless Deluge Automation Engine |  | Deluge Scripts & Advanced Business Logic |  | Cross-Module Data Validation & Auto-Trigger Scripts | Script cross-module data validation rules, automatic milestone unlocks, and project state change triggers. | 4.50 | Customization | High | 3.50 | 6.00 | Automated milestone unlock scripts and cross-module validation operational. | Validation rules documented. | No | Yes | Serverless Deluge Automation Engine › Complex Deluge Business Logic Development | Requires
Elite | Zoho Projects | Custom Deluge Scripting & Enterprise Workflow Functions |  | Serverless Deluge Automation Engine |  | Deluge Scripts & Advanced Business Logic |  | Custom Notification Bots & Automated Executive Summaries | Build automated Deluge bots sending weekly Slack/Cliq/Email portfolio summaries and risk digests. | 4.00 | Customization | Medium | 3.00 | 5.00 | Weekly automated portfolio digest bot active in Cliq / Slack. | Summary report KPI parameters defined. | Yes | Yes | Serverless Deluge Automation Engine › Cross-Module Data Validation & Auto-Trigger Scripts | Requires
Elite | Zoho Projects | Webhooks, REST APIs & DevOps Integrations | GitHub/GitLab/Bitbucket commit syncing, outbound ERP webhooks, and custom REST API endpoints for external data warehouses. | DevOps & Enterprise API Middleware | Bi-directional code repository tracking and real-time ERP event streaming. | Git Integration & Outbound Webhooks | Connect code commits, outbound event streaming, and custom REST APIs. | GitHub, GitLab & Bitbucket DevOps Integrations | Link code commits, pull requests, and git branches directly to Zoho Projects task IDs with auto-status updates. | 4.00 | Integration | High | 3.00 | 5.00 | Git commit linking operational with automatic task status transitions. | GitHub/GitLab repository admin access. | Yes | Yes | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Elite | Zoho Projects | Webhooks, REST APIs & DevOps Integrations |  | DevOps & Enterprise API Middleware |  | Git Integration & Outbound Webhooks |  | Outbound Webhooks & ERP Real-Time Event Streaming | Configure real-time event webhooks pushing project status, milestones, and timesheets to enterprise ERP systems. | 4.00 | Integration | High | 3.00 | 5.00 | Real-time outbound webhooks firing payload to external ERP endpoint. | Target ERP API documentation provided. | Yes | Yes | DevOps & Enterprise API Middleware › GitHub, GitLab & Bitbucket DevOps Integrations | Requires
Elite | Zoho Projects | Webhooks, REST APIs & DevOps Integrations |  | DevOps & Enterprise API Middleware |  | Git Integration & Outbound Webhooks |  | Custom REST API Endpoints & Data Connectors | Develop custom API integrations for third-party billing, procurement, or legacy data warehouses. | 3.50 | Integration | High | 2.50 | 4.50 | Custom REST API connector verified with sample data payload. | External data schema confirmed. | Yes | Yes | DevOps & Enterprise API Middleware › Outbound Webhooks & ERP Real-Time Event Streaming | Requires
Elite | Zoho Projects | Zoho Analytics Executive BI & Portfolio Dashboards | Zoho Analytics relational data modeling, executive portfolio health BI dashboards, and scheduled C-suite KPI digests. | Zoho Analytics Executive BI Engine | Advanced data warehousing and interactive portfolio profitability intelligence for C-suite. | BI Modeling & Executive Dashboards | Deep sync data modeling, profitability dashboards, and automated C-suite digests. | Zoho Analytics Deep Sync & Data Modeling | Connect Zoho Projects database to Zoho Analytics with custom relational data tables and query tables. | 4.00 | Integration | High | 3.00 | 5.00 | Automated data sync established with relational data model in Analytics. | Zoho Analytics enterprise workspace available. | Yes | No | Timesheet Configuration & Work Logging › Standard Timesheet Approval Flow | Requires
Elite | Zoho Projects | Zoho Analytics Executive BI & Portfolio Dashboards |  | Zoho Analytics Executive BI Engine |  | BI Modeling & Executive Dashboards |  | Executive Portfolio Health & Margin Dashboards | Build interactive BI dashboards showing portfolio health, project profitability, burn rates, and team utilization. | 3.50 | Customization | High | 2.50 | 4.50 | Interactive executive BI dashboard active with live portfolio drill-downs. | Executive KPI report layouts agreed. | Yes | No | Zoho Analytics Executive BI Engine › Zoho Analytics Deep Sync & Data Modeling | Requires
Elite | Zoho Projects | Zoho Analytics Executive BI & Portfolio Dashboards |  | Zoho Analytics Executive BI Engine |  | BI Modeling & Executive Dashboards |  | Scheduled C-Suite Reports & KPI Alert Automations | Configure automated PDF/email KPI digests for CEO, PMO Director, and Finance Controller with anomaly alerts. | 3.00 | Configuration | Medium | 2.00 | 3.50 | Scheduled weekly KPI digests active with automated email dispatches. | Executive distribution list provided. | No | No | Zoho Analytics Executive BI Engine › Executive Portfolio Health & Margin Dashboards | Requires
Elite | Zoho Projects | Enterprise Change Management, UAT & 45-Day Hypercare | Multi-tier PMO training academy, 50+ enterprise UAT scenario simulations, and dedicated 45-day Senior Architect hypercare. | Enterprise Change Management & Hypercare | Comprehensive organizational adoption, full UAT simulation, and extended post go-live support. | PMO Academy, Enterprise UAT & 45-Day Care | Conduct PMO academy, 50+ scenario UAT, and 45-day hypercare support. | Multi-Tier PMO & Team Training Academy | Conduct tailored interactive training academies for PMO leads, Project Managers, and Technical Engineers with recorded video SOPs. | 5.50 | Training | High | 4.50 | 7.00 | Completed PMO and engineering training academy with video recordings. | Enterprise configuration completed. | Yes | No | Zoho Analytics Executive BI Engine › Executive Portfolio Health & Margin Dashboards | Requires
Elite | Zoho Projects | Enterprise Change Management, UAT & 45-Day Hypercare |  | Enterprise Change Management & Hypercare |  | PMO Academy, Enterprise UAT & 45-Day Care |  | 50+ Scenario End-to-End UAT Simulation | Rigorous simulation covering scope changes, critical path delays, subcontractor billing, and CRM cutover with real enterprise data. | 4.50 | Validation | High | 3.50 | 6.00 | Formal signed 50+ scenario UAT completion sign-off document. | UAT simulation dataset provided. | Yes | No | Enterprise Change Management & Hypercare › Multi-Tier PMO & Team Training Academy | Requires
Elite | Zoho Projects | Enterprise Change Management, UAT & 45-Day Hypercare |  | Enterprise Change Management & Hypercare |  | PMO Academy, Enterprise UAT & 45-Day Care |  | 45-Day Enterprise Hypercare & Post Go-Live Audit | Dedicated Senior Solution Architect on-call for two full billing cycles, project kickoffs, and PMO optimization reviews. | 6.50 | Support | Medium | 5.00 | 8.00 | Completed 45-day hypercare period and final PMO optimization audit report. | Enterprise production cutover executed. | Yes | No | Enterprise Change Management & Hypercare › 50+ Scenario End-to-End UAT Simulation | Requires
TOTAL ESTIMATED IMPLEMENTATION EFFORT: | [9 empty] | 204.00 Hours

## Basic Plan
Zoho Projects Implementation — Basic Plan Task Sheet
Foundational turnkey setup: 10 Modules ¦ 28 Tasks ¦ 26.0 Hours ¦ Target Timeline: 7–10 Working Days
Product | Module | Module Description | Feature | Feature Description | Parent Task | Parent Task Description | Sub-Task | Sub-Task Description | Estimation Hours | Type | Complexity | Best Case Hours | Worst Case Hours | Deliverables | Prerequisites | Client Input | Script | Depends On | Dependency Type
--- LAYER: BASIC IMPLEMENTATION TASKS ---
Zoho Projects | Organization & Portal Setup | Initial enterprise portal provisioning, branding, regional work calendar, time zone, and transactional email configuration. | Portal & Global Configuration Setup | Foundational portal settings governing all project timelines, operating hours, and system-wide communications. | Portal Setup & Global Settings | Global configuration of portal branding, regional calendar, and delivery notifications. | Portal Profile & Branding | Configure company name, portal logo, favicon, base currency, and default date/time format across the Zoho Projects workspace. | 1.00 | Configuration | Low | 0.80 | 1.20 | Configured branded portal with corporate logo, favicon, and regional date/time standards. | Corporate logo, base currency, and time zone details provided. | Yes | No
Zoho Projects | Organization & Portal Setup |  | Portal & Global Configuration Setup |  | Portal Setup & Global Settings |  | Work Calendar, Timezone & Operating Hours | Define standard organization working days, shift hours, and weekly off days to anchor scheduling and SLA timers. | 1.00 | Configuration | Low | 0.80 | 1.20 | Operating calendar active with official working days and business hours established. | Weekly operating schedule confirmed. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | Organization & Portal Setup |  | Portal & Global Configuration Setup |  | Portal Setup & Global Settings |  | Default Notification Preferences & Email Setup | Set up default email notification digests, project alerts, and system-wide communication preferences for internal users. | 0.50 | Configuration | Low | 0.40 | 0.80 | Standardized notification matrix preventing alert fatigue. | Internal notification rules agreed. | No | No | Portal & Global Configuration Setup › Work Calendar, Timezone & Operating Hours | Requires
Zoho Projects | User Roles & Access Permissions | Role-based access control, standard user profiles, user onboarding, and internal data security boundaries. | User Administration & Role Governance | Establish access boundaries, user licenses, and data visibility rules across project teams. | User Management & Role Matrix | Configure standard profiles, user invitation pipelines, and access boundaries. | User Profiles & Standard Role Matrix | Configure standard role permissions (Admin, Manager, Employee, Contractor) defining view, edit, and delete rights. | 1.00 | Configuration | Medium | 0.80 | 1.50 | Approved standard role permission matrix active in Zoho Projects. | Organizational staffing matrix provided. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | User Roles & Access Permissions |  | User Administration & Role Governance |  | User Management & Role Matrix |  | User Onboarding & Profile Assignment | Invite and provision initial core team members, assign designated roles, and verify profile-level permissions. | 1.00 | Configuration | Low | 0.80 | 1.20 | Core user team onboarded with active portal access. | User email list and role mappings provided. | Yes | No | User Administration & Role Governance › User Profiles & Standard Role Matrix | Requires
Zoho Projects | User Roles & Access Permissions |  | User Administration & Role Governance |  | User Management & Role Matrix |  | Data Access & Security Boundaries | Establish project-level visibility rules ensuring team members only access projects and deliverables assigned to them. | 0.50 | Security | Low | 0.40 | 0.80 | Confidential data isolation verified across sample user accounts. | Project confidentiality policy defined. | No | No | User Administration & Role Governance › User Onboarding & Profile Assignment | Requires
Zoho Projects | Project Structure & Grouping | Organizational portfolio taxonomy, project groups, and master tag categorization. | Portfolio Taxonomy & Categorization | Logical structure grouping client projects by department, industry vertical, or commercial status. | Project Grouping & Taxonomy | Creation of portfolio groups and tagging taxonomy. | Project Groups & Master Tag Library | Set up project groups (e.g., Internal, Client Engagements, R&D) and create standardized master tag library for cross-project filtering. | 1.00 | Configuration | Low | 0.80 | 1.20 | Master tag library and portfolio group categories active. | Departmental taxonomy approved. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | Project Structure & Grouping |  | Portfolio Taxonomy & Categorization |  | Project Grouping & Taxonomy |  | Client Association & Tags | Establish client company profiles within Zoho Projects and link client accounts to corresponding active project workspaces. | 1.00 | Configuration | Low | 0.80 | 1.20 | Initial client account directory linked to corresponding project groups. | Client company list provided. | Yes | No | Portfolio Taxonomy & Categorization › Project Groups & Master Tag Library | Requires
Zoho Projects | Standard Project Template Architecture | Creation of standardized project templates, repeatable task lists, and Rapid project provisioning. | Project Template & Delivery Standardization | Turnkey templates codifying standard operating procedures for rapid, consistent project kickoffs. | Template Engineering & Instantiation | Build and calibrate master project delivery templates. | Master Project Template Creation (Up to 5) | Build up to 5 standardized project delivery templates with pre-configured milestones, task lists, and recurring deliverables. | 1.50 | Configuration | Medium | 1.20 | 2.00 | 5 production-ready project templates configured in the template gallery. | Standard WBS deliverable flows provided. | Yes | No | Portfolio Taxonomy & Categorization › Project Groups & Master Tag Library | Requires
Zoho Projects | Standard Project Template Architecture |  | Project Template & Delivery Standardization |  | Template Engineering & Instantiation |  | Task List Standardization & Plain/Kanban Views | Configure task list categorization and optimize Classic, Plain, and Kanban board task views within standard templates. | 1.00 | Configuration | Low | 0.80 | 1.20 | Standardized task lists with customized Kanban board columns. | Task status definitions agreed. | No | No | Project Template & Delivery Standardization › Master Project Template Creation (Up to 5) | Requires
Zoho Projects | Standard Project Template Architecture |  | Project Template & Delivery Standardization |  | Template Engineering & Instantiation |  | Template Cloning & Instantiation | Validate template-to-project creation workflow, ensuring tasks, milestones, and assigned roles clone accurately upon instantiation. | 0.50 | Validation | Low | 0.40 | 0.80 | Successful test instantiation of a live project from master template. | Templates completed. | No | No | Project Template & Delivery Standardization › Task List Standardization & Plain/Kanban Views | Requires
Zoho Projects | Task Breakdown Structure (WBS) & Milestones | Decomposition of complex client contracts into milestones, parent tasks, and sub-tasks with percentage progress rollups. | Work Breakdown Structure (WBS) Engine | Multi-tier deliverable decomposition ensuring complete milestone traceability. | WBS & Milestone Planning | Structure milestones, nested subtasks, and progress tracking. | Milestone & Phase Configuration | Establish project milestones linked to deliverable target dates, designated milestone owners, and flag milestone completion criteria. | 1.00 | Configuration | Low | 0.80 | 1.20 | Milestone timeline established across sample delivery project. | Target deliverable dates defined. | Yes | No | Project Template & Delivery Standardization › Template Cloning & Instantiation | Requires
Zoho Projects | Task Breakdown Structure (WBS) & Milestones |  | Work Breakdown Structure (WBS) Engine |  | WBS & Milestone Planning |  | Task & Nested Subtask Hierarchy | Configure multi-level nested subtasks under primary deliverable tasks with automatic progress percentage rollups to parent tasks. | 1.00 | Configuration | Medium | 0.80 | 1.50 | Multi-tier task hierarchy active with dynamic percentage rollups. | Nested task breakdown agreed. | No | No | Work Breakdown Structure (WBS) Engine › Milestone & Phase Configuration | Requires
Zoho Projects | Task Breakdown Structure (WBS) & Milestones |  | Work Breakdown Structure (WBS) Engine |  | WBS & Milestone Planning |  | Task Priority, Tags & Recurrence | Setup priority flags (None, Low, Medium, High), task recurrence schedules, and tag assignments for operational sorting. | 0.50 | Configuration | Low | 0.40 | 0.80 | Priority and recurring task schedules active. | Recurrence intervals provided. | No | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Task Dependencies & Gantt Visualization | Chronological Gantt chart configuration, predecessor dependency logic, and dynamic schedule cascading. | Gantt Timeline & Predecessor Logic | Visual chronological scheduling ensuring tasks execute in contractual sequence. | Gantt Scheduling & Dependency Linking | Set up Gantt charts, FS dependency logic, and timeline cascading. | Finish-to-Start (FS) Dependencies | Configure standard Finish-to-Start (FS) dependency links between predecessor and successor tasks across project task lists. | 1.00 | Configuration | Low | 0.80 | 1.20 | Predecessor-successor links active across task timelines. | Deliverable sequence logic confirmed. | No | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Task Dependencies & Gantt Visualization |  | Gantt Timeline & Predecessor Logic |  | Gantt Scheduling & Dependency Linking |  | Chronological Gantt Chart View & Export | Configure chronological Gantt timeline display, milestone markers, dependency lines, and PDF/image export options. | 1.00 | Configuration | Low | 0.80 | 1.20 | Interactive Gantt view verified with working PDF export. | Tasks and dependencies populated. | No | No | Gantt Timeline & Predecessor Logic › Finish-to-Start (FS) Dependencies | Requires
Zoho Projects | Task Dependencies & Gantt Visualization |  | Gantt Timeline & Predecessor Logic |  | Gantt Scheduling & Dependency Linking |  | Schedule Cascading Verification | Test and verify dynamic date shifting: ensure that extending a predecessor task deadline automatically shifts dependent successor dates. | 0.50 | Validation | Low | 0.40 | 0.80 | Dynamic date cascading verified with zero scheduling breaks. | Gantt dependencies active. | No | No | Gantt Timeline & Predecessor Logic › Chronological Gantt Chart View & Export | Requires
Zoho Projects | Timesheets & Work Logging | Time tracking, live stopwatch timer, daily/weekly timesheet grids, and basic approval workflows. | Time Tracking & Timesheet Logging | Captures staff execution hours against tasks and milestones for operational auditing. | Timesheet Configuration & Work Logging | Configure time logging grids, timers, and manager review. | Daily & Weekly Timesheet Logging | Configure timesheet entry grid allowing team members to log actual work hours against tasks with mandatory activity notes. | 1.00 | Configuration | Low | 0.80 | 1.20 | Timesheet grid operational with daily/weekly view options. | Time tracking policy established. | Yes | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Timesheets & Work Logging |  | Time Tracking & Timesheet Logging |  | Timesheet Configuration & Work Logging |  | Live Stopwatch Timer & Billable Classification | Configure desktop and mobile in-app live stopwatch timers and configure Billable vs Non-Billable hour categorization. | 0.50 | Configuration | Low | 0.40 | 0.80 | Live timer functional with billable status flags. | Billable criteria defined. | No | No | Time Tracking & Timesheet Logging › Daily & Weekly Timesheet Logging | Requires
Zoho Projects | Timesheets & Work Logging |  | Time Tracking & Timesheet Logging |  | Timesheet Configuration & Work Logging |  | Standard Timesheet Approval Flow | Set up project manager timesheet review workflow allowing PMs to approve, edit, or reject submitted time logs prior to closing. | 1.00 | Configuration | Medium | 0.80 | 1.20 | Managerial timesheet approval queue active. | Approval hierarchy agreed. | Yes | No | Time Tracking & Timesheet Logging › Live Stopwatch Timer & Billable Classification | Requires
Zoho Projects | Documents, Zoho Meeting & File Repository | Project documentation repository, document versioning, and Zoho collaboration app interconnect. | Document Storage & Meeting Collaboration | Centralized project asset repository and integrated virtual meeting tools. | Document Repository & Collaboration Tools | Structure folders, document versions, and virtual meetings. | Project Folder & Document Hierarchy | Configure structured project document folder hierarchy (e.g., Deliverables, Meeting Notes, Client Specs) for file centralization. | 1.00 | Configuration | Low | 0.80 | 1.20 | Standardized folder structure embedded across project workspaces. | Folder taxonomy approved. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | Documents, Zoho Meeting & File Repository |  | Document Storage & Meeting Collaboration |  | Document Repository & Collaboration Tools |  | File Uploads, Previews & Version History | Configure file attachment rules, inline document previewing, and document version history tracking on tasks and project docs. | 1.00 | Configuration | Low | 0.80 | 1.20 | File versioning verified with multi-format previews. | File storage policy confirmed. | No | No | Document Storage & Meeting Collaboration › Project Folder & Document Hierarchy | Requires
Zoho Projects | Documents, Zoho Meeting & File Repository |  | Document Storage & Meeting Collaboration |  | Document Repository & Collaboration Tools |  | Zoho Meeting & Zoho Mail Alias Setup | Connect Zoho Meeting for 1-click project conferencing and configure project email aliases for direct email-to-task routing. | 0.50 | Integration | Low | 0.40 | 0.80 | Meeting launch button and inbound project email alias functional. | Zoho Meeting / Mail licenses available. | No | No | Document Storage & Meeting Collaboration › File Uploads, Previews & Version History | Requires
Zoho Projects | Basic Issue / Bug Tracking | Centralized defect capture, severity matrices, and standard issue resolution lifecycles. | Issue & Bug Tracking Engine | Systematic issue logging and resolution workflows linked to project deliverables. | Issue Tracking & Resolution Workflow | Set up bug categories, severity levels, and resolution states. | Issue Logging & Classification Setup | Activate Issue Tracker module, configure custom bug severity levels, classifications, and link issues directly to affected tasks. | 1.00 | Configuration | Low | 0.80 | 1.20 | Issue logging interface active with custom severity tags. | Issue classification rules agreed. | Yes | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Basic Issue / Bug Tracking |  | Issue & Bug Tracking Engine |  | Issue Tracking & Resolution Workflow |  | Standard Issue Lifecycle States & Workflow | Configure issue resolution states (Open, In Investigation, In Fix, Verified, Closed) with mandatory technician assignment. | 1.00 | Configuration | Low | 0.80 | 1.20 | Governed issue lifecycle workflow active. | Issue workflow states confirmed. | No | No | Issue & Bug Tracking Engine › Issue Logging & Classification Setup | Requires
Zoho Projects | Team Training, Walkthrough & SOPs | Role-based end-user training workshops, hands-on user walkthroughs, and standard operating procedure quick guides. | User Enablement & Operational Handover | Structured training sprints ensuring rapid, high-confidence team adoption. | Training Academy & Delivery Handover | Conduct PM training, team work logging sessions, and deliver SOP documentation. | Project Manager Hands-On Training | Conduct live interactive training for Project Managers on project creation, Gantt scheduling, task assignment, and timesheets. | 1.50 | Training | Medium | 1.20 | 2.00 | Completed training session for PMs with recorded walkthrough video. | Basic configuration completed. | Yes | No | Timesheet Configuration & Work Logging › Standard Timesheet Approval Flow | Requires
Zoho Projects | Team Training, Walkthrough & SOPs |  | User Enablement & Operational Handover |  | Training Academy & Delivery Handover |  | Team Member Task & Time Tracking Training | Deliver hands-on training for team members covering task updates, checklist completion, document uploads, and stopwatch work logging. | 1.50 | Training | Low | 1.20 | 2.00 | Completed team member training session with attendance log. | PM training completed. | Yes | No | User Enablement & Operational Handover › Project Manager Hands-On Training | Requires
Zoho Projects | Team Training, Walkthrough & SOPs |  | User Enablement & Operational Handover |  | Training Academy & Delivery Handover |  | Standard Operating Procedure (SOP) Quick Guide | Provide a tailored, concise PDF quick-reference SOP guide covering daily task tracking, timesheets, and support issue workflows. | 1.00 | Documentation | Low | 0.80 | 1.20 | Branded PDF SOP manual delivered to client leadership. | Workflows finalized. | No | No | User Enablement & Operational Handover › Team Member Task & Time Tracking Training | Requires
TOTAL ESTIMATED IMPLEMENTATION EFFORT: | [8 empty] | 26.00 Hours

## Professional Plan (Cumulative)
Zoho Projects Implementation — Professional Plan Task Sheet (Cumulative)
Cumulative turnkey delivery: Basic Foundation (28 Tasks, 26.0h) + Professional Workflows (33 Tasks, 63.0h) ¦ Total: 61 Tasks, 89.0 Hours ¦ Target: 15–20 Working Days
Product | Module | Module Description | Feature | Feature Description | Parent Task | Parent Task Description | Sub-Task | Sub-Task Description | Estimation Hours | Type | Complexity | Best Case Hours | Worst Case Hours | Deliverables | Prerequisites | Client Input | Script | Depends On | Dependency Type
--- LAYER: BASIC IMPLEMENTATION TASKS ---
Zoho Projects | Organization & Portal Setup | Initial enterprise portal provisioning, branding, regional work calendar, time zone, and transactional email configuration. | Portal & Global Configuration Setup | Foundational portal settings governing all project timelines, operating hours, and system-wide communications. | Portal Setup & Global Settings | Global configuration of portal branding, regional calendar, and delivery notifications. | Portal Profile & Branding | Configure company name, portal logo, favicon, base currency, and default date/time format across the Zoho Projects workspace. | 1.00 | Configuration | Low | 0.80 | 1.20 | Configured branded portal with corporate logo, favicon, and regional date/time standards. | Corporate logo, base currency, and time zone details provided. | Yes | No
Zoho Projects | Organization & Portal Setup |  | Portal & Global Configuration Setup |  | Portal Setup & Global Settings |  | Work Calendar, Timezone & Operating Hours | Define standard organization working days, shift hours, and weekly off days to anchor scheduling and SLA timers. | 1.00 | Configuration | Low | 0.80 | 1.20 | Operating calendar active with official working days and business hours established. | Weekly operating schedule confirmed. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | Organization & Portal Setup |  | Portal & Global Configuration Setup |  | Portal Setup & Global Settings |  | Default Notification Preferences & Email Setup | Set up default email notification digests, project alerts, and system-wide communication preferences for internal users. | 0.50 | Configuration | Low | 0.40 | 0.80 | Standardized notification matrix preventing alert fatigue. | Internal notification rules agreed. | No | No | Portal & Global Configuration Setup › Work Calendar, Timezone & Operating Hours | Requires
Zoho Projects | User Roles & Access Permissions | Role-based access control, standard user profiles, user onboarding, and internal data security boundaries. | User Administration & Role Governance | Establish access boundaries, user licenses, and data visibility rules across project teams. | User Management & Role Matrix | Configure standard profiles, user invitation pipelines, and access boundaries. | User Profiles & Standard Role Matrix | Configure standard role permissions (Admin, Manager, Employee, Contractor) defining view, edit, and delete rights. | 1.00 | Configuration | Medium | 0.80 | 1.50 | Approved standard role permission matrix active in Zoho Projects. | Organizational staffing matrix provided. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | User Roles & Access Permissions |  | User Administration & Role Governance |  | User Management & Role Matrix |  | User Onboarding & Profile Assignment | Invite and provision initial core team members, assign designated roles, and verify profile-level permissions. | 1.00 | Configuration | Low | 0.80 | 1.20 | Core user team onboarded with active portal access. | User email list and role mappings provided. | Yes | No | User Administration & Role Governance › User Profiles & Standard Role Matrix | Requires
Zoho Projects | User Roles & Access Permissions |  | User Administration & Role Governance |  | User Management & Role Matrix |  | Data Access & Security Boundaries | Establish project-level visibility rules ensuring team members only access projects and deliverables assigned to them. | 0.50 | Security | Low | 0.40 | 0.80 | Confidential data isolation verified across sample user accounts. | Project confidentiality policy defined. | No | No | User Administration & Role Governance › User Onboarding & Profile Assignment | Requires
Zoho Projects | Project Structure & Grouping | Organizational portfolio taxonomy, project groups, and master tag categorization. | Portfolio Taxonomy & Categorization | Logical structure grouping client projects by department, industry vertical, or commercial status. | Project Grouping & Taxonomy | Creation of portfolio groups and tagging taxonomy. | Project Groups & Master Tag Library | Set up project groups (e.g., Internal, Client Engagements, R&D) and create standardized master tag library for cross-project filtering. | 1.00 | Configuration | Low | 0.80 | 1.20 | Master tag library and portfolio group categories active. | Departmental taxonomy approved. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | Project Structure & Grouping |  | Portfolio Taxonomy & Categorization |  | Project Grouping & Taxonomy |  | Client Association & Tags | Establish client company profiles within Zoho Projects and link client accounts to corresponding active project workspaces. | 1.00 | Configuration | Low | 0.80 | 1.20 | Initial client account directory linked to corresponding project groups. | Client company list provided. | Yes | No | Portfolio Taxonomy & Categorization › Project Groups & Master Tag Library | Requires
Zoho Projects | Standard Project Template Architecture | Creation of standardized project templates, repeatable task lists, and Rapid project provisioning. | Project Template & Delivery Standardization | Turnkey templates codifying standard operating procedures for rapid, consistent project kickoffs. | Template Engineering & Instantiation | Build and calibrate master project delivery templates. | Master Project Template Creation (Up to 5) | Build up to 5 standardized project delivery templates with pre-configured milestones, task lists, and recurring deliverables. | 1.50 | Configuration | Medium | 1.20 | 2.00 | 5 production-ready project templates configured in the template gallery. | Standard WBS deliverable flows provided. | Yes | No | Portfolio Taxonomy & Categorization › Project Groups & Master Tag Library | Requires
Zoho Projects | Standard Project Template Architecture |  | Project Template & Delivery Standardization |  | Template Engineering & Instantiation |  | Task List Standardization & Plain/Kanban Views | Configure task list categorization and optimize Classic, Plain, and Kanban board task views within standard templates. | 1.00 | Configuration | Low | 0.80 | 1.20 | Standardized task lists with customized Kanban board columns. | Task status definitions agreed. | No | No | Project Template & Delivery Standardization › Master Project Template Creation (Up to 5) | Requires
Zoho Projects | Standard Project Template Architecture |  | Project Template & Delivery Standardization |  | Template Engineering & Instantiation |  | Template Cloning & Instantiation | Validate template-to-project creation workflow, ensuring tasks, milestones, and assigned roles clone accurately upon instantiation. | 0.50 | Validation | Low | 0.40 | 0.80 | Successful test instantiation of a live project from master template. | Templates completed. | No | No | Project Template & Delivery Standardization › Task List Standardization & Plain/Kanban Views | Requires
Zoho Projects | Task Breakdown Structure (WBS) & Milestones | Decomposition of complex client contracts into milestones, parent tasks, and sub-tasks with percentage progress rollups. | Work Breakdown Structure (WBS) Engine | Multi-tier deliverable decomposition ensuring complete milestone traceability. | WBS & Milestone Planning | Structure milestones, nested subtasks, and progress tracking. | Milestone & Phase Configuration | Establish project milestones linked to deliverable target dates, designated milestone owners, and flag milestone completion criteria. | 1.00 | Configuration | Low | 0.80 | 1.20 | Milestone timeline established across sample delivery project. | Target deliverable dates defined. | Yes | No | Project Template & Delivery Standardization › Template Cloning & Instantiation | Requires
Zoho Projects | Task Breakdown Structure (WBS) & Milestones |  | Work Breakdown Structure (WBS) Engine |  | WBS & Milestone Planning |  | Task & Nested Subtask Hierarchy | Configure multi-level nested subtasks under primary deliverable tasks with automatic progress percentage rollups to parent tasks. | 1.00 | Configuration | Medium | 0.80 | 1.50 | Multi-tier task hierarchy active with dynamic percentage rollups. | Nested task breakdown agreed. | No | No | Work Breakdown Structure (WBS) Engine › Milestone & Phase Configuration | Requires
Zoho Projects | Task Breakdown Structure (WBS) & Milestones |  | Work Breakdown Structure (WBS) Engine |  | WBS & Milestone Planning |  | Task Priority, Tags & Recurrence | Setup priority flags (None, Low, Medium, High), task recurrence schedules, and tag assignments for operational sorting. | 0.50 | Configuration | Low | 0.40 | 0.80 | Priority and recurring task schedules active. | Recurrence intervals provided. | No | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Task Dependencies & Gantt Visualization | Chronological Gantt chart configuration, predecessor dependency logic, and dynamic schedule cascading. | Gantt Timeline & Predecessor Logic | Visual chronological scheduling ensuring tasks execute in contractual sequence. | Gantt Scheduling & Dependency Linking | Set up Gantt charts, FS dependency logic, and timeline cascading. | Finish-to-Start (FS) Dependencies | Configure standard Finish-to-Start (FS) dependency links between predecessor and successor tasks across project task lists. | 1.00 | Configuration | Low | 0.80 | 1.20 | Predecessor-successor links active across task timelines. | Deliverable sequence logic confirmed. | No | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Task Dependencies & Gantt Visualization |  | Gantt Timeline & Predecessor Logic |  | Gantt Scheduling & Dependency Linking |  | Chronological Gantt Chart View & Export | Configure chronological Gantt timeline display, milestone markers, dependency lines, and PDF/image export options. | 1.00 | Configuration | Low | 0.80 | 1.20 | Interactive Gantt view verified with working PDF export. | Tasks and dependencies populated. | No | No | Gantt Timeline & Predecessor Logic › Finish-to-Start (FS) Dependencies | Requires
Zoho Projects | Task Dependencies & Gantt Visualization |  | Gantt Timeline & Predecessor Logic |  | Gantt Scheduling & Dependency Linking |  | Schedule Cascading Verification | Test and verify dynamic date shifting: ensure that extending a predecessor task deadline automatically shifts dependent successor dates. | 0.50 | Validation | Low | 0.40 | 0.80 | Dynamic date cascading verified with zero scheduling breaks. | Gantt dependencies active. | No | No | Gantt Timeline & Predecessor Logic › Chronological Gantt Chart View & Export | Requires
Zoho Projects | Timesheets & Work Logging | Time tracking, live stopwatch timer, daily/weekly timesheet grids, and basic approval workflows. | Time Tracking & Timesheet Logging | Captures staff execution hours against tasks and milestones for operational auditing. | Timesheet Configuration & Work Logging | Configure time logging grids, timers, and manager review. | Daily & Weekly Timesheet Logging | Configure timesheet entry grid allowing team members to log actual work hours against tasks with mandatory activity notes. | 1.00 | Configuration | Low | 0.80 | 1.20 | Timesheet grid operational with daily/weekly view options. | Time tracking policy established. | Yes | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Timesheets & Work Logging |  | Time Tracking & Timesheet Logging |  | Timesheet Configuration & Work Logging |  | Live Stopwatch Timer & Billable Classification | Configure desktop and mobile in-app live stopwatch timers and configure Billable vs Non-Billable hour categorization. | 0.50 | Configuration | Low | 0.40 | 0.80 | Live timer functional with billable status flags. | Billable criteria defined. | No | No | Time Tracking & Timesheet Logging › Daily & Weekly Timesheet Logging | Requires
Zoho Projects | Timesheets & Work Logging |  | Time Tracking & Timesheet Logging |  | Timesheet Configuration & Work Logging |  | Standard Timesheet Approval Flow | Set up project manager timesheet review workflow allowing PMs to approve, edit, or reject submitted time logs prior to closing. | 1.00 | Configuration | Medium | 0.80 | 1.20 | Managerial timesheet approval queue active. | Approval hierarchy agreed. | Yes | No | Time Tracking & Timesheet Logging › Live Stopwatch Timer & Billable Classification | Requires
Zoho Projects | Documents, Zoho Meeting & File Repository | Project documentation repository, document versioning, and Zoho collaboration app interconnect. | Document Storage & Meeting Collaboration | Centralized project asset repository and integrated virtual meeting tools. | Document Repository & Collaboration Tools | Structure folders, document versions, and virtual meetings. | Project Folder & Document Hierarchy | Configure structured project document folder hierarchy (e.g., Deliverables, Meeting Notes, Client Specs) for file centralization. | 1.00 | Configuration | Low | 0.80 | 1.20 | Standardized folder structure embedded across project workspaces. | Folder taxonomy approved. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | Documents, Zoho Meeting & File Repository |  | Document Storage & Meeting Collaboration |  | Document Repository & Collaboration Tools |  | File Uploads, Previews & Version History | Configure file attachment rules, inline document previewing, and document version history tracking on tasks and project docs. | 1.00 | Configuration | Low | 0.80 | 1.20 | File versioning verified with multi-format previews. | File storage policy confirmed. | No | No | Document Storage & Meeting Collaboration › Project Folder & Document Hierarchy | Requires
Zoho Projects | Documents, Zoho Meeting & File Repository |  | Document Storage & Meeting Collaboration |  | Document Repository & Collaboration Tools |  | Zoho Meeting & Zoho Mail Alias Setup | Connect Zoho Meeting for 1-click project conferencing and configure project email aliases for direct email-to-task routing. | 0.50 | Integration | Low | 0.40 | 0.80 | Meeting launch button and inbound project email alias functional. | Zoho Meeting / Mail licenses available. | No | No | Document Storage & Meeting Collaboration › File Uploads, Previews & Version History | Requires
Zoho Projects | Basic Issue / Bug Tracking | Centralized defect capture, severity matrices, and standard issue resolution lifecycles. | Issue & Bug Tracking Engine | Systematic issue logging and resolution workflows linked to project deliverables. | Issue Tracking & Resolution Workflow | Set up bug categories, severity levels, and resolution states. | Issue Logging & Classification Setup | Activate Issue Tracker module, configure custom bug severity levels, classifications, and link issues directly to affected tasks. | 1.00 | Configuration | Low | 0.80 | 1.20 | Issue logging interface active with custom severity tags. | Issue classification rules agreed. | Yes | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Basic Issue / Bug Tracking |  | Issue & Bug Tracking Engine |  | Issue Tracking & Resolution Workflow |  | Standard Issue Lifecycle States & Workflow | Configure issue resolution states (Open, In Investigation, In Fix, Verified, Closed) with mandatory technician assignment. | 1.00 | Configuration | Low | 0.80 | 1.20 | Governed issue lifecycle workflow active. | Issue workflow states confirmed. | No | No | Issue & Bug Tracking Engine › Issue Logging & Classification Setup | Requires
Zoho Projects | Team Training, Walkthrough & SOPs | Role-based end-user training workshops, hands-on user walkthroughs, and standard operating procedure quick guides. | User Enablement & Operational Handover | Structured training sprints ensuring rapid, high-confidence team adoption. | Training Academy & Delivery Handover | Conduct PM training, team work logging sessions, and deliver SOP documentation. | Project Manager Hands-On Training | Conduct live interactive training for Project Managers on project creation, Gantt scheduling, task assignment, and timesheets. | 1.50 | Training | Medium | 1.20 | 2.00 | Completed training session for PMs with recorded walkthrough video. | Basic configuration completed. | Yes | No | Timesheet Configuration & Work Logging › Standard Timesheet Approval Flow | Requires
Zoho Projects | Team Training, Walkthrough & SOPs |  | User Enablement & Operational Handover |  | Training Academy & Delivery Handover |  | Team Member Task & Time Tracking Training | Deliver hands-on training for team members covering task updates, checklist completion, document uploads, and stopwatch work logging. | 1.50 | Training | Low | 1.20 | 2.00 | Completed team member training session with attendance log. | PM training completed. | Yes | No | User Enablement & Operational Handover › Project Manager Hands-On Training | Requires
Zoho Projects | Team Training, Walkthrough & SOPs |  | User Enablement & Operational Handover |  | Training Academy & Delivery Handover |  | Standard Operating Procedure (SOP) Quick Guide | Provide a tailored, concise PDF quick-reference SOP guide covering daily task tracking, timesheets, and support issue workflows. | 1.00 | Documentation | Low | 0.80 | 1.20 | Branded PDF SOP manual delivered to client leadership. | Workflows finalized. | No | No | User Enablement & Operational Handover › Team Member Task & Time Tracking Training | Requires
--- LAYER: PROFESSIONAL IMPLEMENTATION TASKS ---
Zoho Projects | Multi-Department Workspace & Custom Domain | Enterprise multi-department portfolio structures, custom branded portal domains, and multi-regional holiday calendars. | Multi-Department Workspace Architecture | Segmented project workspaces across business units with dedicated custom domains. | Departmental Portfolio & Domain Branding | Structure cross-departmental portfolios, custom domain mapping, and regional calendars. | Multi-Department Portfolio Structure | Structure segmented project workspaces, tags, and access boundaries across discrete business units or branch operations. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Multi-departmental portfolio structure active with segregated views. | Departmental organization chart approved. | Yes | No | Portfolio Taxonomy & Categorization › Project Groups & Master Tag Library | Requires
Zoho Projects | Multi-Department Workspace & Custom Domain |  | Multi-Department Workspace Architecture |  | Departmental Portfolio & Domain Branding |  | Custom Domain Mapping & Portal URL Branding | Configure custom domain mapping (e.g., projects.company.com) with SSL certificate provisioning and white-label URL access. | 1.50 | Security | Medium | 1.00 | 2.00 | Active branded portal URL with verified SSL certificate. | DNS CNAME record access provided by client IT. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | Multi-Department Workspace & Custom Domain |  | Multi-Department Workspace Architecture |  | Departmental Portfolio & Domain Branding |  | Multi-Regional Holiday Calendars | Set up multiple regional and international holiday calendars linked to specific team members to automate scheduling across distributed offices. | 1.00 | Configuration | Low | 0.80 | 1.50 | Multi-regional holiday calendars mapped to user groups. | Regional holiday schedules provided. | Yes | No | Portal & Global Configuration Setup › Work Calendar, Timezone & Operating Hours | Requires
Zoho Projects | Granular Roles, Profiles & Field Security | Granular permission sets, external client user permissions, and confidential field masking. | Granular Profile & Permission Matrix | Fine-grained security governing module access, rate visibility, and project confidentiality. | Access Control & Field Security | Build custom profile matrices, external client roles, and field masking. | Granular Custom Role & Designation Matrices | Build tailored permission profiles (PM, Lead Architect, Financial Controller, Contractor) with granular create/edit/delete limits. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Detailed custom profile matrix active with role assignments. | Role permissions policy approved. | Yes | No | User Administration & Role Governance › User Profiles & Standard Role Matrix | Requires
Zoho Projects | Granular Roles, Profiles & Field Security |  | Granular Profile & Permission Matrix |  | Access Control & Field Security |  | Client User Setup & External Permissions | Configure external Client User profiles with restricted view permissions limited strictly to designated deliverables and milestones. | 1.50 | Configuration | Medium | 1.00 | 2.00 | Client external user profile configured and tested. | Client visibility requirements defined. | Yes | No | Granular Profile & Permission Matrix › Granular Custom Role & Designation Matrices | Requires
Zoho Projects | Granular Roles, Profiles & Field Security |  | Granular Profile & Permission Matrix |  | Access Control & Field Security |  | Confidential Project Security & Field Masking | Enforce field-level security and confidential project flags to restrict budget, billing rates, and contractual fields from non-finance staff. | 1.00 | Security | Medium | 0.80 | 1.50 | Field masking verified across restricted employee roles. | Confidential data fields identified. | No | No | Granular Profile & Permission Matrix › Client User Setup & External Permissions | Requires
Zoho Projects | Multi-Template Library & Dependency Logic | Extended template repository (up to 20+ templates), advanced predecessor logic, and automatic schedule shifting. | Advanced Template & Scheduling Engine | Complex dependency modeling and dynamic schedule shifting across diverse project typologies. | Template Library & Dependency Architecture | Build extended template gallery and all four dependency logic models. | Extended Project Template Library (Up to 20+) | Develop and calibrate up to 20 comprehensive project delivery templates across diverse client engagement models. | 2.50 | Configuration | Medium | 2.00 | 3.50 | Complete library of up to 20 reusable project templates. | Standardized WBS workflows across departments. | Yes | No | Project Template & Delivery Standardization › Master Project Template Creation (Up to 5) | Requires
Zoho Projects | Multi-Template Library & Dependency Logic |  | Advanced Template & Scheduling Engine |  | Template Library & Dependency Architecture |  | Advanced Dependency Architecture (FS, SS, FF, SF) | Configure all four dependency logic models (Finish-to-Start, Start-to-Start, Finish-to-Finish, Start-to-Finish) with lead and lag time settings. | 1.50 | Configuration | Medium | 1.00 | 2.00 | 4-tier dependency logic validated on complex template schedules. | Dependency logic mapped. | No | No | Advanced Template & Scheduling Engine › Extended Project Template Library (Up to 20+) | Requires
Zoho Projects | Multi-Template Library & Dependency Logic |  | Advanced Template & Scheduling Engine |  | Template Library & Dependency Architecture |  | Strict Project Scheduling & Auto-Rescheduling | Implement strict scheduling constraints and automated rescheduling rules when deliverable timelines or predecessor tasks shift. | 1.50 | Configuration | Medium | 1.00 | 2.00 | Strict auto-rescheduling rules operational. | Scheduling rules agreed. | No | No | Advanced Template & Scheduling Engine › Advanced Dependency Architecture (FS, SS, FF, SF) | Requires
Zoho Projects | Task Breakdown Structure (WBS), Views & Dynamic Layouts | Custom project and task fields, dynamic layout visibility rules, custom status workflows, and embedded web tabs. | Custom Data Architecture & Dynamic Layouts | Tailor data structures and conditional visibility across project layouts. | Custom Fields & Dynamic Layout Rules | Configure custom fields, visibility rules, and web tabs. | Custom Project & Task Field Architecture | Build custom fields (currency, formula, user lookup, dropdown, date) across projects, tasks, and milestone layouts. | 2.50 | Customization | Medium | 2.00 | 3.00 | Custom field data architecture active across modules. | Custom field data dictionary approved. | Yes | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Task Breakdown Structure (WBS), Views & Dynamic Layouts |  | Custom Data Architecture & Dynamic Layouts |  | Custom Fields & Dynamic Layout Rules |  | Dynamic Layout Rules & Conditional Visibility | Set up conditional field rules showing or hiding task parameters dynamically based on project type, priority, or stage selection. | 2.00 | Customization | Medium | 1.50 | 2.50 | Dynamic layout rules active and verified. | Field conditional logic mapped. | No | No | Custom Data Architecture & Dynamic Layouts › Custom Project & Task Field Architecture | Requires
Zoho Projects | Task Breakdown Structure (WBS), Views & Dynamic Layouts |  | Custom Data Architecture & Dynamic Layouts |  | Custom Fields & Dynamic Layout Rules |  | Custom Status Workflows & Custom Web Tabs | Design custom status workflows per project category and embed custom web tabs linking external portals or live dashboards directly in projects. | 1.50 | Customization | Low | 1.00 | 2.00 | Custom status flows and embedded web tabs functional. | External web tab URLs confirmed. | Yes | No | Custom Data Architecture & Dynamic Layouts › Dynamic Layout Rules & Conditional Visibility | Requires
Zoho Projects | Milestone & Task Blueprints (Process Governance) | Visual state machine governance, mandatory checklist validations, digital sign-offs, and automated stage actions. | Visual State Machine Blueprints | Enforce operational compliance and prevent unauthorized task progression through rigid stage-gates. | Blueprint Design & Gatekeeping | Design visual state machines, sign-offs, and automated transitions. | Task Status Blueprint Design | Design visual state machine Blueprints defining allowed status transitions and authorized role transitions for project tasks. | 3.00 | Customization | High | 2.50 | 4.00 | Active Task Status Blueprint controlling lifecycle states. | Task lifecycle state transitions documented. | Yes | No | Custom Data Architecture & Dynamic Layouts › Custom Status Workflows & Custom Web Tabs | Requires
Zoho Projects | Milestone & Task Blueprints (Process Governance) |  | Visual State Machine Blueprints |  | Blueprint Design & Gatekeeping |  | Milestone Gatekeeping & Deliverable Sign-Offs | Configure mandatory transition criteria requiring document attachments, sign-off notes, and mandatory checklist completion before stage advancement. | 2.00 | Customization | Medium | 1.50 | 2.50 | Mandatory gatekeeping rules preventing premature task closure. | Mandatory deliverable checklists agreed. | No | No | Visual State Machine Blueprints › Task Status Blueprint Design | Requires
Zoho Projects | Milestone & Task Blueprints (Process Governance) |  | Visual State Machine Blueprints |  | Blueprint Design & Gatekeeping |  | Automated Blueprint Actions, Macros & Alerts | Attach automated field updates, email alerts, and webhook triggers that execute dynamically during Blueprint stage transitions. | 2.00 | Customization | Medium | 1.50 | 2.50 | Automated transition triggers functional on status changes. | Notification recipients confirmed. | No | No | Visual State Machine Blueprints › Milestone Gatekeeping & Deliverable Sign-Offs | Requires
Zoho Projects | Interactive Gantt Scheduling & Project Baselines | Critical Path Method (CPM) calculation, multi-version baseline comparisons, and portfolio Gantt views. | Critical Path (CPM) & Baseline Variance | Schedule risk optimization, zero-slack bottlenecks, and contractual baseline variance tracking. | CPM Scheduling & Baseline Management | Set up CPM calculation, baselines, and multi-project Gantt. | Advanced Gantt Configuration & Critical Path | Configure dynamic Critical Path identification, automatic schedule compression options, and zero-slack task highlights. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Dynamic Critical Path highlighted across project schedules. | Task dependencies configured. | No | No | Advanced Template & Scheduling Engine › Advanced Dependency Architecture (FS, SS, FF, SF) | Requires
Zoho Projects | Interactive Gantt Scheduling & Project Baselines |  | Critical Path (CPM) & Baseline Variance |  | CPM Scheduling & Baseline Management |  | Project Baseline Tracking & Variance Analysis | Lock initial project schedule baseline and configure visual variance comparison bars tracking deviations between planned vs actual dates. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Locked baseline version with visual Gantt variance overlays. | Baseline schedule approved. | Yes | No | Critical Path (CPM) & Baseline Variance › Advanced Gantt Configuration & Critical Path | Requires
Zoho Projects | Interactive Gantt Scheduling & Project Baselines |  | Critical Path (CPM) & Baseline Variance |  | CPM Scheduling & Baseline Management |  | Multi-Project Portfolio Gantt View | Configure cross-project Chronological Gantt overview allowing management to track overlapping timelines across the entire active portfolio. | 1.50 | Configuration | Low | 1.00 | 2.00 | Cross-project portfolio Gantt dashboard operational. | Multiple active projects populated. | No | No | Critical Path (CPM) & Baseline Variance › Project Baseline Tracking & Variance Analysis | Requires
Zoho Projects | Resource Capacity Planning & Workload Balancing | Resource utilization heatmaps, daily/weekly capacity allocation limits, burnout detection, and Zoho People leave sync. | Resource Capacity & Utilization Engine | Real-time visibility into staff availability and cross-project workload balancing. | Resource Leveling & People Sync | Configure utilization heatmaps, workload balancing, and leave calendar sync. | Resource Allocation & Heatmap Setup | Configure color-coded Resource Utilization Chart showing daily and weekly allocation hours against predefined working limits. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Active Resource Utilization Heatmap showing real-time staff loads. | Staff working hours and role allocation agreed. | Yes | No | Portal & Global Configuration Setup › Work Calendar, Timezone & Operating Hours | Requires
Zoho Projects | Resource Capacity Planning & Workload Balancing |  | Resource Capacity & Utilization Engine |  | Resource Leveling & People Sync |  | Workload Leveling & Over-Allocation Mitigation | Establish resource allocation rules and visual warning thresholds flagging team members scheduled above 100% capacity. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Over-allocation alerts active with drag-and-drop task re-leveling. | Capacity thresholds confirmed. | No | No | Resource Capacity & Utilization Engine › Resource Allocation & Heatmap Setup | Requires
Zoho Projects | Resource Capacity Planning & Workload Balancing |  | Resource Capacity & Utilization Engine |  | Resource Leveling & People Sync |  | Zoho People Leave Integration & Shift Sync | Connect Zoho People to dynamically ingest employee approved leave, holidays, and working shifts directly into project scheduling calendars. | 1.50 | Integration | Medium | 1.00 | 2.00 | Bi-directional leave sync active between Zoho People and Projects. | Zoho People organization access available. | Yes | No | Resource Capacity & Utilization Engine › Workload Leveling & Over-Allocation Mitigation | Requires
Zoho Projects | Advanced Timesheets, Multi-Tier Billing & Approvals | Staff/Role/Project hourly billing rates, mobile tracking, multi-tier approval chains, and payroll lock periods. | Multi-Tier Billing Rates & Approvals | Commercial rate card modeling and multi-stage financial approval chains. | Billing Rates & Governance Approval | Set up rate cards, mobile timers, and lockdown periods. | Multi-Tier Billing Rates Architecture | Configure Staff-Based, Role-Based, and Project-Based hourly billing rates for accurate client invoicing and costing. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Configured rate cards active across all billing roles. | Contractual billing rate schedule provided. | Yes | No | Time Tracking & Timesheet Logging › Daily & Weekly Timesheet Logging | Requires
Zoho Projects | Advanced Timesheets, Multi-Tier Billing & Approvals |  | Multi-Tier Billing Rates & Approvals |  | Billing Rates & Governance Approval |  | Live Stopwatch Timer & Mobile Tracking | Configure in-app live multi-timer stopwatch and mobile time tracking with automated background work logging. | 1.50 | Configuration | Low | 1.00 | 2.00 | Mobile time tracking verified with background work sync. | Mobile app access enabled. | No | No | Multi-Tier Billing Rates & Approvals › Multi-Tier Billing Rates Architecture | Requires
Zoho Projects | Advanced Timesheets, Multi-Tier Billing & Approvals |  | Multi-Tier Billing Rates & Approvals |  | Billing Rates & Governance Approval |  | Multi-Tier Timesheet Approval & Lock Periods | Establish multi-stage approval workflows (PM -> Finance Head) with automated timesheet lockdown at payroll cutoff. | 2.50 | Configuration | Medium | 2.00 | 3.00 | Automated payroll lock periods active preventing past edits. | Payroll cutoff cycle confirmed. | Yes | No | Multi-Tier Billing Rates & Approvals › Live Stopwatch Timer & Mobile Tracking | Requires
Zoho Projects | Issue / Bug SLA Management & Business Rules | Custom bug tracking layouts, SLA targets, automated business assignment rules, and escalation hierarchies. | Issue SLA & Business Automation Rules | Enforce strict contractual response and resolution SLAs with automated multi-tier escalations. | SLA Governance & Issue Automation | Set up custom bug layouts, SLA targets, and escalation triggers. | Custom Issue Layouts, Email-to-Issue & Views | Build custom bug tracking layouts, custom severity matrices, email-to-issue alias, and issue-to-task linking. | 2.00 | Customization | Medium | 1.50 | 2.50 | Custom issue tracking layout with inbound email parser. | Issue fields dictionary approved. | Yes | No | Issue & Bug Tracking Engine › Issue Logging & Classification Setup | Requires
Zoho Projects | Issue / Bug SLA Management & Business Rules |  | Issue SLA & Business Automation Rules |  | SLA Governance & Issue Automation |  | SLA Management & Business Rules Auto-Assign | Configure formal SLAs (First Response & Resolution) and automated business rules for auto-assignment and field updates. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Active SLA policies with automatic technician assignment. | Contractual SLA targets confirmed. | Yes | No | Issue SLA & Business Automation Rules › Custom Issue Layouts, Email-to-Issue & Views | Requires
Zoho Projects | Issue / Bug SLA Management & Business Rules |  | Issue SLA & Business Automation Rules |  | SLA Governance & Issue Automation |  | Multi-Level Escalation Automation Rules | Automate multi-tier escalation triggers routing SLA-breaching issues to senior leadership via high-priority alerts. | 1.50 | Configuration | Low | 1.00 | 2.00 | Multi-level escalation rules active on SLA breach. | Escalation recipients documented. | No | No | Issue SLA & Business Automation Rules › SLA Management & Business Rules Auto-Assign | Requires
Zoho Projects | Ecosystem Integrations: Zoho Books, CRM & Office | Direct Zoho Books timesheet-to-invoice sync, Zoho CRM Deal Won auto-provisioning, and MS 365 / Google Workspace sync. | Ecosystem Closed-Loop Integrations | Bridge sales pipeline handoff, back-office billing, and team collaboration into an automated pipeline. | Books, CRM & Office Cloud Interconnect | Connect Books timesheet invoicing, CRM deal templates, and Office suites. | Direct Zoho Books Timesheet-to-Invoice Sync | Configure bi-directional sync linking Zoho Projects with Zoho Books/Invoice for one-click invoice generation from approved hours. | 2.50 | Integration | High | 2.00 | 3.50 | 1-click client invoice generation operational from approved timesheets. | Zoho Books organization access and chart of accounts confirmed. | Yes | No | Multi-Tier Billing Rates & Approvals › Multi-Tier Timesheet Approval & Lock Periods | Requires
Zoho Projects | Ecosystem Integrations: Zoho Books, CRM & Office |  | Ecosystem Closed-Loop Integrations |  | Books, CRM & Office Cloud Interconnect |  | Zoho CRM Deal-to-Project Auto-Creation | Auto-instantiate project templates upon Deal Won in Zoho CRM, syncing client details, scope deliverables, and target dates. | 2.00 | Integration | Medium | 1.50 | 2.50 | Automated project provisioning verified upon CRM Deal Won trigger. | Zoho CRM deal stages and field mapping agreed. | Yes | No | Project Template & Delivery Standardization › Master Project Template Creation (Up to 5) | Requires
Zoho Projects | Ecosystem Integrations: Zoho Books, CRM & Office |  | Ecosystem Closed-Loop Integrations |  | Books, CRM & Office Cloud Interconnect |  | Google Workspace & Microsoft 365 Integration | Connect Google Drive/Calendar and Microsoft Teams/Outlook/OneDrive/SharePoint with CSV & MS Project (.mpp) migration. | 2.50 | Integration | Medium | 2.00 | 3.00 | MS 365 / Google Workspace sync active with document repository. | Cloud tenant admin credentials available. | Yes | No | Document Storage & Meeting Collaboration › Project Folder & Document Hierarchy | Requires
Zoho Projects | Departmental Training, Simulation & 30-Day Hypercare | Departmental role-based training workshops, 25+ real-data UAT scenario simulations, and dedicated 30-day post go-live hypercare. | Professional Change Management & Hypercare | Rigorous UAT validation and dedicated consultant support ensuring zero-defect go-live. | Training Sprints, UAT & Post-Go-Live Care | Deliver training academies, simulate UAT, and provide 30-day hypercare. | Departmental Training Sprints | Deliver specialized training workshops for Project Managers, Resource Planners, and Finance/Billing administrators. | 2.50 | Training | Medium | 2.00 | 3.00 | Completed training sprints for PMs, resource planners, and billing team. | All professional configuration modules validated. | Yes | No | Ecosystem Closed-Loop Integrations › Direct Zoho Books Timesheet-to-Invoice Sync | Requires
Zoho Projects | Departmental Training, Simulation & 30-Day Hypercare |  | Professional Change Management & Hypercare |  | Training Sprints, UAT & Post-Go-Live Care |  | User Acceptance Testing (UAT) Simulation | Simulate 25+ real client delivery scenarios: scope changes, baseline shifts, contractor timesheets, and invoice sync. | 2.00 | Validation | Medium | 1.50 | 2.50 | Formal signed UAT sign-off document with zero open defects. | UAT test cases and client test team available. | Yes | No | Professional Change Management & Hypercare › Departmental Training Sprints | Requires
Zoho Projects | Departmental Training, Simulation & 30-Day Hypercare |  | Professional Change Management & Hypercare |  | Training Sprints, UAT & Post-Go-Live Care |  | 30-Day Post Go-Live Hypercare | Dedicated consultant on-call support during first monthly project closing, client billing run, and resource reviews. | 1.50 | Support | Low | 1.00 | 2.00 | Completed 30-day hypercare period with monthly project closing report. | Production cutover executed. | Yes | No | Professional Change Management & Hypercare › User Acceptance Testing (UAT) Simulation | Requires
TOTAL ESTIMATED IMPLEMENTATION EFFORT: | [8 empty] | 89.00 Hours

## Elite Plan (Cumulative)
Zoho Projects Implementation — Elite Plan Task Sheet (Cumulative)
Complete enterprise delivery: Basic Foundation (26.0h) + Professional Workflows (63.0h) + Elite Governance & EVM (115.0h) ¦ Total: 95 Tasks, 204.0 Hours ¦ Target: 30–45 Working Days
Product | Module | Module Description | Feature | Feature Description | Parent Task | Parent Task Description | Sub-Task | Sub-Task Description | Estimation Hours | Type | Complexity | Best Case Hours | Worst Case Hours | Deliverables | Prerequisites | Client Input | Script | Depends On | Dependency Type
--- LAYER: BASIC IMPLEMENTATION TASKS ---
Zoho Projects | Organization & Portal Setup | Initial enterprise portal provisioning, branding, regional work calendar, time zone, and transactional email configuration. | Portal & Global Configuration Setup | Foundational portal settings governing all project timelines, operating hours, and system-wide communications. | Portal Setup & Global Settings | Global configuration of portal branding, regional calendar, and delivery notifications. | Portal Profile & Branding | Configure company name, portal logo, favicon, base currency, and default date/time format across the Zoho Projects workspace. | 1.00 | Configuration | Low | 0.80 | 1.20 | Configured branded portal with corporate logo, favicon, and regional date/time standards. | Corporate logo, base currency, and time zone details provided. | Yes | No
Zoho Projects | Organization & Portal Setup |  | Portal & Global Configuration Setup |  | Portal Setup & Global Settings |  | Work Calendar, Timezone & Operating Hours | Define standard organization working days, shift hours, and weekly off days to anchor scheduling and SLA timers. | 1.00 | Configuration | Low | 0.80 | 1.20 | Operating calendar active with official working days and business hours established. | Weekly operating schedule confirmed. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | Organization & Portal Setup |  | Portal & Global Configuration Setup |  | Portal Setup & Global Settings |  | Default Notification Preferences & Email Setup | Set up default email notification digests, project alerts, and system-wide communication preferences for internal users. | 0.50 | Configuration | Low | 0.40 | 0.80 | Standardized notification matrix preventing alert fatigue. | Internal notification rules agreed. | No | No | Portal & Global Configuration Setup › Work Calendar, Timezone & Operating Hours | Requires
Zoho Projects | User Roles & Access Permissions | Role-based access control, standard user profiles, user onboarding, and internal data security boundaries. | User Administration & Role Governance | Establish access boundaries, user licenses, and data visibility rules across project teams. | User Management & Role Matrix | Configure standard profiles, user invitation pipelines, and access boundaries. | User Profiles & Standard Role Matrix | Configure standard role permissions (Admin, Manager, Employee, Contractor) defining view, edit, and delete rights. | 1.00 | Configuration | Medium | 0.80 | 1.50 | Approved standard role permission matrix active in Zoho Projects. | Organizational staffing matrix provided. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | User Roles & Access Permissions |  | User Administration & Role Governance |  | User Management & Role Matrix |  | User Onboarding & Profile Assignment | Invite and provision initial core team members, assign designated roles, and verify profile-level permissions. | 1.00 | Configuration | Low | 0.80 | 1.20 | Core user team onboarded with active portal access. | User email list and role mappings provided. | Yes | No | User Administration & Role Governance › User Profiles & Standard Role Matrix | Requires
Zoho Projects | User Roles & Access Permissions |  | User Administration & Role Governance |  | User Management & Role Matrix |  | Data Access & Security Boundaries | Establish project-level visibility rules ensuring team members only access projects and deliverables assigned to them. | 0.50 | Security | Low | 0.40 | 0.80 | Confidential data isolation verified across sample user accounts. | Project confidentiality policy defined. | No | No | User Administration & Role Governance › User Onboarding & Profile Assignment | Requires
Zoho Projects | Project Structure & Grouping | Organizational portfolio taxonomy, project groups, and master tag categorization. | Portfolio Taxonomy & Categorization | Logical structure grouping client projects by department, industry vertical, or commercial status. | Project Grouping & Taxonomy | Creation of portfolio groups and tagging taxonomy. | Project Groups & Master Tag Library | Set up project groups (e.g., Internal, Client Engagements, R&D) and create standardized master tag library for cross-project filtering. | 1.00 | Configuration | Low | 0.80 | 1.20 | Master tag library and portfolio group categories active. | Departmental taxonomy approved. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | Project Structure & Grouping |  | Portfolio Taxonomy & Categorization |  | Project Grouping & Taxonomy |  | Client Association & Tags | Establish client company profiles within Zoho Projects and link client accounts to corresponding active project workspaces. | 1.00 | Configuration | Low | 0.80 | 1.20 | Initial client account directory linked to corresponding project groups. | Client company list provided. | Yes | No | Portfolio Taxonomy & Categorization › Project Groups & Master Tag Library | Requires
Zoho Projects | Standard Project Template Architecture | Creation of standardized project templates, repeatable task lists, and Rapid project provisioning. | Project Template & Delivery Standardization | Turnkey templates codifying standard operating procedures for rapid, consistent project kickoffs. | Template Engineering & Instantiation | Build and calibrate master project delivery templates. | Master Project Template Creation (Up to 5) | Build up to 5 standardized project delivery templates with pre-configured milestones, task lists, and recurring deliverables. | 1.50 | Configuration | Medium | 1.20 | 2.00 | 5 production-ready project templates configured in the template gallery. | Standard WBS deliverable flows provided. | Yes | No | Portfolio Taxonomy & Categorization › Project Groups & Master Tag Library | Requires
Zoho Projects | Standard Project Template Architecture |  | Project Template & Delivery Standardization |  | Template Engineering & Instantiation |  | Task List Standardization & Plain/Kanban Views | Configure task list categorization and optimize Classic, Plain, and Kanban board task views within standard templates. | 1.00 | Configuration | Low | 0.80 | 1.20 | Standardized task lists with customized Kanban board columns. | Task status definitions agreed. | No | No | Project Template & Delivery Standardization › Master Project Template Creation (Up to 5) | Requires
Zoho Projects | Standard Project Template Architecture |  | Project Template & Delivery Standardization |  | Template Engineering & Instantiation |  | Template Cloning & Instantiation | Validate template-to-project creation workflow, ensuring tasks, milestones, and assigned roles clone accurately upon instantiation. | 0.50 | Validation | Low | 0.40 | 0.80 | Successful test instantiation of a live project from master template. | Templates completed. | No | No | Project Template & Delivery Standardization › Task List Standardization & Plain/Kanban Views | Requires
Zoho Projects | Task Breakdown Structure (WBS) & Milestones | Decomposition of complex client contracts into milestones, parent tasks, and sub-tasks with percentage progress rollups. | Work Breakdown Structure (WBS) Engine | Multi-tier deliverable decomposition ensuring complete milestone traceability. | WBS & Milestone Planning | Structure milestones, nested subtasks, and progress tracking. | Milestone & Phase Configuration | Establish project milestones linked to deliverable target dates, designated milestone owners, and flag milestone completion criteria. | 1.00 | Configuration | Low | 0.80 | 1.20 | Milestone timeline established across sample delivery project. | Target deliverable dates defined. | Yes | No | Project Template & Delivery Standardization › Template Cloning & Instantiation | Requires
Zoho Projects | Task Breakdown Structure (WBS) & Milestones |  | Work Breakdown Structure (WBS) Engine |  | WBS & Milestone Planning |  | Task & Nested Subtask Hierarchy | Configure multi-level nested subtasks under primary deliverable tasks with automatic progress percentage rollups to parent tasks. | 1.00 | Configuration | Medium | 0.80 | 1.50 | Multi-tier task hierarchy active with dynamic percentage rollups. | Nested task breakdown agreed. | No | No | Work Breakdown Structure (WBS) Engine › Milestone & Phase Configuration | Requires
Zoho Projects | Task Breakdown Structure (WBS) & Milestones |  | Work Breakdown Structure (WBS) Engine |  | WBS & Milestone Planning |  | Task Priority, Tags & Recurrence | Setup priority flags (None, Low, Medium, High), task recurrence schedules, and tag assignments for operational sorting. | 0.50 | Configuration | Low | 0.40 | 0.80 | Priority and recurring task schedules active. | Recurrence intervals provided. | No | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Task Dependencies & Gantt Visualization | Chronological Gantt chart configuration, predecessor dependency logic, and dynamic schedule cascading. | Gantt Timeline & Predecessor Logic | Visual chronological scheduling ensuring tasks execute in contractual sequence. | Gantt Scheduling & Dependency Linking | Set up Gantt charts, FS dependency logic, and timeline cascading. | Finish-to-Start (FS) Dependencies | Configure standard Finish-to-Start (FS) dependency links between predecessor and successor tasks across project task lists. | 1.00 | Configuration | Low | 0.80 | 1.20 | Predecessor-successor links active across task timelines. | Deliverable sequence logic confirmed. | No | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Task Dependencies & Gantt Visualization |  | Gantt Timeline & Predecessor Logic |  | Gantt Scheduling & Dependency Linking |  | Chronological Gantt Chart View & Export | Configure chronological Gantt timeline display, milestone markers, dependency lines, and PDF/image export options. | 1.00 | Configuration | Low | 0.80 | 1.20 | Interactive Gantt view verified with working PDF export. | Tasks and dependencies populated. | No | No | Gantt Timeline & Predecessor Logic › Finish-to-Start (FS) Dependencies | Requires
Zoho Projects | Task Dependencies & Gantt Visualization |  | Gantt Timeline & Predecessor Logic |  | Gantt Scheduling & Dependency Linking |  | Schedule Cascading Verification | Test and verify dynamic date shifting: ensure that extending a predecessor task deadline automatically shifts dependent successor dates. | 0.50 | Validation | Low | 0.40 | 0.80 | Dynamic date cascading verified with zero scheduling breaks. | Gantt dependencies active. | No | No | Gantt Timeline & Predecessor Logic › Chronological Gantt Chart View & Export | Requires
Zoho Projects | Timesheets & Work Logging | Time tracking, live stopwatch timer, daily/weekly timesheet grids, and basic approval workflows. | Time Tracking & Timesheet Logging | Captures staff execution hours against tasks and milestones for operational auditing. | Timesheet Configuration & Work Logging | Configure time logging grids, timers, and manager review. | Daily & Weekly Timesheet Logging | Configure timesheet entry grid allowing team members to log actual work hours against tasks with mandatory activity notes. | 1.00 | Configuration | Low | 0.80 | 1.20 | Timesheet grid operational with daily/weekly view options. | Time tracking policy established. | Yes | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Timesheets & Work Logging |  | Time Tracking & Timesheet Logging |  | Timesheet Configuration & Work Logging |  | Live Stopwatch Timer & Billable Classification | Configure desktop and mobile in-app live stopwatch timers and configure Billable vs Non-Billable hour categorization. | 0.50 | Configuration | Low | 0.40 | 0.80 | Live timer functional with billable status flags. | Billable criteria defined. | No | No | Time Tracking & Timesheet Logging › Daily & Weekly Timesheet Logging | Requires
Zoho Projects | Timesheets & Work Logging |  | Time Tracking & Timesheet Logging |  | Timesheet Configuration & Work Logging |  | Standard Timesheet Approval Flow | Set up project manager timesheet review workflow allowing PMs to approve, edit, or reject submitted time logs prior to closing. | 1.00 | Configuration | Medium | 0.80 | 1.20 | Managerial timesheet approval queue active. | Approval hierarchy agreed. | Yes | No | Time Tracking & Timesheet Logging › Live Stopwatch Timer & Billable Classification | Requires
Zoho Projects | Documents, Zoho Meeting & File Repository | Project documentation repository, document versioning, and Zoho collaboration app interconnect. | Document Storage & Meeting Collaboration | Centralized project asset repository and integrated virtual meeting tools. | Document Repository & Collaboration Tools | Structure folders, document versions, and virtual meetings. | Project Folder & Document Hierarchy | Configure structured project document folder hierarchy (e.g., Deliverables, Meeting Notes, Client Specs) for file centralization. | 1.00 | Configuration | Low | 0.80 | 1.20 | Standardized folder structure embedded across project workspaces. | Folder taxonomy approved. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | Documents, Zoho Meeting & File Repository |  | Document Storage & Meeting Collaboration |  | Document Repository & Collaboration Tools |  | File Uploads, Previews & Version History | Configure file attachment rules, inline document previewing, and document version history tracking on tasks and project docs. | 1.00 | Configuration | Low | 0.80 | 1.20 | File versioning verified with multi-format previews. | File storage policy confirmed. | No | No | Document Storage & Meeting Collaboration › Project Folder & Document Hierarchy | Requires
Zoho Projects | Documents, Zoho Meeting & File Repository |  | Document Storage & Meeting Collaboration |  | Document Repository & Collaboration Tools |  | Zoho Meeting & Zoho Mail Alias Setup | Connect Zoho Meeting for 1-click project conferencing and configure project email aliases for direct email-to-task routing. | 0.50 | Integration | Low | 0.40 | 0.80 | Meeting launch button and inbound project email alias functional. | Zoho Meeting / Mail licenses available. | No | No | Document Storage & Meeting Collaboration › File Uploads, Previews & Version History | Requires
Zoho Projects | Basic Issue / Bug Tracking | Centralized defect capture, severity matrices, and standard issue resolution lifecycles. | Issue & Bug Tracking Engine | Systematic issue logging and resolution workflows linked to project deliverables. | Issue Tracking & Resolution Workflow | Set up bug categories, severity levels, and resolution states. | Issue Logging & Classification Setup | Activate Issue Tracker module, configure custom bug severity levels, classifications, and link issues directly to affected tasks. | 1.00 | Configuration | Low | 0.80 | 1.20 | Issue logging interface active with custom severity tags. | Issue classification rules agreed. | Yes | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Basic Issue / Bug Tracking |  | Issue & Bug Tracking Engine |  | Issue Tracking & Resolution Workflow |  | Standard Issue Lifecycle States & Workflow | Configure issue resolution states (Open, In Investigation, In Fix, Verified, Closed) with mandatory technician assignment. | 1.00 | Configuration | Low | 0.80 | 1.20 | Governed issue lifecycle workflow active. | Issue workflow states confirmed. | No | No | Issue & Bug Tracking Engine › Issue Logging & Classification Setup | Requires
Zoho Projects | Team Training, Walkthrough & SOPs | Role-based end-user training workshops, hands-on user walkthroughs, and standard operating procedure quick guides. | User Enablement & Operational Handover | Structured training sprints ensuring rapid, high-confidence team adoption. | Training Academy & Delivery Handover | Conduct PM training, team work logging sessions, and deliver SOP documentation. | Project Manager Hands-On Training | Conduct live interactive training for Project Managers on project creation, Gantt scheduling, task assignment, and timesheets. | 1.50 | Training | Medium | 1.20 | 2.00 | Completed training session for PMs with recorded walkthrough video. | Basic configuration completed. | Yes | No | Timesheet Configuration & Work Logging › Standard Timesheet Approval Flow | Requires
Zoho Projects | Team Training, Walkthrough & SOPs |  | User Enablement & Operational Handover |  | Training Academy & Delivery Handover |  | Team Member Task & Time Tracking Training | Deliver hands-on training for team members covering task updates, checklist completion, document uploads, and stopwatch work logging. | 1.50 | Training | Low | 1.20 | 2.00 | Completed team member training session with attendance log. | PM training completed. | Yes | No | User Enablement & Operational Handover › Project Manager Hands-On Training | Requires
Zoho Projects | Team Training, Walkthrough & SOPs |  | User Enablement & Operational Handover |  | Training Academy & Delivery Handover |  | Standard Operating Procedure (SOP) Quick Guide | Provide a tailored, concise PDF quick-reference SOP guide covering daily task tracking, timesheets, and support issue workflows. | 1.00 | Documentation | Low | 0.80 | 1.20 | Branded PDF SOP manual delivered to client leadership. | Workflows finalized. | No | No | User Enablement & Operational Handover › Team Member Task & Time Tracking Training | Requires
--- LAYER: PROFESSIONAL IMPLEMENTATION TASKS ---
Zoho Projects | Multi-Department Workspace & Custom Domain | Enterprise multi-department portfolio structures, custom branded portal domains, and multi-regional holiday calendars. | Multi-Department Workspace Architecture | Segmented project workspaces across business units with dedicated custom domains. | Departmental Portfolio & Domain Branding | Structure cross-departmental portfolios, custom domain mapping, and regional calendars. | Multi-Department Portfolio Structure | Structure segmented project workspaces, tags, and access boundaries across discrete business units or branch operations. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Multi-departmental portfolio structure active with segregated views. | Departmental organization chart approved. | Yes | No | Portfolio Taxonomy & Categorization › Project Groups & Master Tag Library | Requires
Zoho Projects | Multi-Department Workspace & Custom Domain |  | Multi-Department Workspace Architecture |  | Departmental Portfolio & Domain Branding |  | Custom Domain Mapping & Portal URL Branding | Configure custom domain mapping (e.g., projects.company.com) with SSL certificate provisioning and white-label URL access. | 1.50 | Security | Medium | 1.00 | 2.00 | Active branded portal URL with verified SSL certificate. | DNS CNAME record access provided by client IT. | Yes | No | Portal & Global Configuration Setup › Portal Profile & Branding | Requires
Zoho Projects | Multi-Department Workspace & Custom Domain |  | Multi-Department Workspace Architecture |  | Departmental Portfolio & Domain Branding |  | Multi-Regional Holiday Calendars | Set up multiple regional and international holiday calendars linked to specific team members to automate scheduling across distributed offices. | 1.00 | Configuration | Low | 0.80 | 1.50 | Multi-regional holiday calendars mapped to user groups. | Regional holiday schedules provided. | Yes | No | Portal & Global Configuration Setup › Work Calendar, Timezone & Operating Hours | Requires
Zoho Projects | Granular Roles, Profiles & Field Security | Granular permission sets, external client user permissions, and confidential field masking. | Granular Profile & Permission Matrix | Fine-grained security governing module access, rate visibility, and project confidentiality. | Access Control & Field Security | Build custom profile matrices, external client roles, and field masking. | Granular Custom Role & Designation Matrices | Build tailored permission profiles (PM, Lead Architect, Financial Controller, Contractor) with granular create/edit/delete limits. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Detailed custom profile matrix active with role assignments. | Role permissions policy approved. | Yes | No | User Administration & Role Governance › User Profiles & Standard Role Matrix | Requires
Zoho Projects | Granular Roles, Profiles & Field Security |  | Granular Profile & Permission Matrix |  | Access Control & Field Security |  | Client User Setup & External Permissions | Configure external Client User profiles with restricted view permissions limited strictly to designated deliverables and milestones. | 1.50 | Configuration | Medium | 1.00 | 2.00 | Client external user profile configured and tested. | Client visibility requirements defined. | Yes | No | Granular Profile & Permission Matrix › Granular Custom Role & Designation Matrices | Requires
Zoho Projects | Granular Roles, Profiles & Field Security |  | Granular Profile & Permission Matrix |  | Access Control & Field Security |  | Confidential Project Security & Field Masking | Enforce field-level security and confidential project flags to restrict budget, billing rates, and contractual fields from non-finance staff. | 1.00 | Security | Medium | 0.80 | 1.50 | Field masking verified across restricted employee roles. | Confidential data fields identified. | No | No | Granular Profile & Permission Matrix › Client User Setup & External Permissions | Requires
Zoho Projects | Multi-Template Library & Dependency Logic | Extended template repository (up to 20+ templates), advanced predecessor logic, and automatic schedule shifting. | Advanced Template & Scheduling Engine | Complex dependency modeling and dynamic schedule shifting across diverse project typologies. | Template Library & Dependency Architecture | Build extended template gallery and all four dependency logic models. | Extended Project Template Library (Up to 20+) | Develop and calibrate up to 20 comprehensive project delivery templates across diverse client engagement models. | 2.50 | Configuration | Medium | 2.00 | 3.50 | Complete library of up to 20 reusable project templates. | Standardized WBS workflows across departments. | Yes | No | Project Template & Delivery Standardization › Master Project Template Creation (Up to 5) | Requires
Zoho Projects | Multi-Template Library & Dependency Logic |  | Advanced Template & Scheduling Engine |  | Template Library & Dependency Architecture |  | Advanced Dependency Architecture (FS, SS, FF, SF) | Configure all four dependency logic models (Finish-to-Start, Start-to-Start, Finish-to-Finish, Start-to-Finish) with lead and lag time settings. | 1.50 | Configuration | Medium | 1.00 | 2.00 | 4-tier dependency logic validated on complex template schedules. | Dependency logic mapped. | No | No | Advanced Template & Scheduling Engine › Extended Project Template Library (Up to 20+) | Requires
Zoho Projects | Multi-Template Library & Dependency Logic |  | Advanced Template & Scheduling Engine |  | Template Library & Dependency Architecture |  | Strict Project Scheduling & Auto-Rescheduling | Implement strict scheduling constraints and automated rescheduling rules when deliverable timelines or predecessor tasks shift. | 1.50 | Configuration | Medium | 1.00 | 2.00 | Strict auto-rescheduling rules operational. | Scheduling rules agreed. | No | No | Advanced Template & Scheduling Engine › Advanced Dependency Architecture (FS, SS, FF, SF) | Requires
Zoho Projects | Task Breakdown Structure (WBS), Views & Dynamic Layouts | Custom project and task fields, dynamic layout visibility rules, custom status workflows, and embedded web tabs. | Custom Data Architecture & Dynamic Layouts | Tailor data structures and conditional visibility across project layouts. | Custom Fields & Dynamic Layout Rules | Configure custom fields, visibility rules, and web tabs. | Custom Project & Task Field Architecture | Build custom fields (currency, formula, user lookup, dropdown, date) across projects, tasks, and milestone layouts. | 2.50 | Customization | Medium | 2.00 | 3.00 | Custom field data architecture active across modules. | Custom field data dictionary approved. | Yes | No | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Task Breakdown Structure (WBS), Views & Dynamic Layouts |  | Custom Data Architecture & Dynamic Layouts |  | Custom Fields & Dynamic Layout Rules |  | Dynamic Layout Rules & Conditional Visibility | Set up conditional field rules showing or hiding task parameters dynamically based on project type, priority, or stage selection. | 2.00 | Customization | Medium | 1.50 | 2.50 | Dynamic layout rules active and verified. | Field conditional logic mapped. | No | No | Custom Data Architecture & Dynamic Layouts › Custom Project & Task Field Architecture | Requires
Zoho Projects | Task Breakdown Structure (WBS), Views & Dynamic Layouts |  | Custom Data Architecture & Dynamic Layouts |  | Custom Fields & Dynamic Layout Rules |  | Custom Status Workflows & Custom Web Tabs | Design custom status workflows per project category and embed custom web tabs linking external portals or live dashboards directly in projects. | 1.50 | Customization | Low | 1.00 | 2.00 | Custom status flows and embedded web tabs functional. | External web tab URLs confirmed. | Yes | No | Custom Data Architecture & Dynamic Layouts › Dynamic Layout Rules & Conditional Visibility | Requires
Zoho Projects | Milestone & Task Blueprints (Process Governance) | Visual state machine governance, mandatory checklist validations, digital sign-offs, and automated stage actions. | Visual State Machine Blueprints | Enforce operational compliance and prevent unauthorized task progression through rigid stage-gates. | Blueprint Design & Gatekeeping | Design visual state machines, sign-offs, and automated transitions. | Task Status Blueprint Design | Design visual state machine Blueprints defining allowed status transitions and authorized role transitions for project tasks. | 3.00 | Customization | High | 2.50 | 4.00 | Active Task Status Blueprint controlling lifecycle states. | Task lifecycle state transitions documented. | Yes | No | Custom Data Architecture & Dynamic Layouts › Custom Status Workflows & Custom Web Tabs | Requires
Zoho Projects | Milestone & Task Blueprints (Process Governance) |  | Visual State Machine Blueprints |  | Blueprint Design & Gatekeeping |  | Milestone Gatekeeping & Deliverable Sign-Offs | Configure mandatory transition criteria requiring document attachments, sign-off notes, and mandatory checklist completion before stage advancement. | 2.00 | Customization | Medium | 1.50 | 2.50 | Mandatory gatekeeping rules preventing premature task closure. | Mandatory deliverable checklists agreed. | No | No | Visual State Machine Blueprints › Task Status Blueprint Design | Requires
Zoho Projects | Milestone & Task Blueprints (Process Governance) |  | Visual State Machine Blueprints |  | Blueprint Design & Gatekeeping |  | Automated Blueprint Actions, Macros & Alerts | Attach automated field updates, email alerts, and webhook triggers that execute dynamically during Blueprint stage transitions. | 2.00 | Customization | Medium | 1.50 | 2.50 | Automated transition triggers functional on status changes. | Notification recipients confirmed. | No | No | Visual State Machine Blueprints › Milestone Gatekeeping & Deliverable Sign-Offs | Requires
Zoho Projects | Interactive Gantt Scheduling & Project Baselines | Critical Path Method (CPM) calculation, multi-version baseline comparisons, and portfolio Gantt views. | Critical Path (CPM) & Baseline Variance | Schedule risk optimization, zero-slack bottlenecks, and contractual baseline variance tracking. | CPM Scheduling & Baseline Management | Set up CPM calculation, baselines, and multi-project Gantt. | Advanced Gantt Configuration & Critical Path | Configure dynamic Critical Path identification, automatic schedule compression options, and zero-slack task highlights. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Dynamic Critical Path highlighted across project schedules. | Task dependencies configured. | No | No | Advanced Template & Scheduling Engine › Advanced Dependency Architecture (FS, SS, FF, SF) | Requires
Zoho Projects | Interactive Gantt Scheduling & Project Baselines |  | Critical Path (CPM) & Baseline Variance |  | CPM Scheduling & Baseline Management |  | Project Baseline Tracking & Variance Analysis | Lock initial project schedule baseline and configure visual variance comparison bars tracking deviations between planned vs actual dates. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Locked baseline version with visual Gantt variance overlays. | Baseline schedule approved. | Yes | No | Critical Path (CPM) & Baseline Variance › Advanced Gantt Configuration & Critical Path | Requires
Zoho Projects | Interactive Gantt Scheduling & Project Baselines |  | Critical Path (CPM) & Baseline Variance |  | CPM Scheduling & Baseline Management |  | Multi-Project Portfolio Gantt View | Configure cross-project Chronological Gantt overview allowing management to track overlapping timelines across the entire active portfolio. | 1.50 | Configuration | Low | 1.00 | 2.00 | Cross-project portfolio Gantt dashboard operational. | Multiple active projects populated. | No | No | Critical Path (CPM) & Baseline Variance › Project Baseline Tracking & Variance Analysis | Requires
Zoho Projects | Resource Capacity Planning & Workload Balancing | Resource utilization heatmaps, daily/weekly capacity allocation limits, burnout detection, and Zoho People leave sync. | Resource Capacity & Utilization Engine | Real-time visibility into staff availability and cross-project workload balancing. | Resource Leveling & People Sync | Configure utilization heatmaps, workload balancing, and leave calendar sync. | Resource Allocation & Heatmap Setup | Configure color-coded Resource Utilization Chart showing daily and weekly allocation hours against predefined working limits. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Active Resource Utilization Heatmap showing real-time staff loads. | Staff working hours and role allocation agreed. | Yes | No | Portal & Global Configuration Setup › Work Calendar, Timezone & Operating Hours | Requires
Zoho Projects | Resource Capacity Planning & Workload Balancing |  | Resource Capacity & Utilization Engine |  | Resource Leveling & People Sync |  | Workload Leveling & Over-Allocation Mitigation | Establish resource allocation rules and visual warning thresholds flagging team members scheduled above 100% capacity. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Over-allocation alerts active with drag-and-drop task re-leveling. | Capacity thresholds confirmed. | No | No | Resource Capacity & Utilization Engine › Resource Allocation & Heatmap Setup | Requires
Zoho Projects | Resource Capacity Planning & Workload Balancing |  | Resource Capacity & Utilization Engine |  | Resource Leveling & People Sync |  | Zoho People Leave Integration & Shift Sync | Connect Zoho People to dynamically ingest employee approved leave, holidays, and working shifts directly into project scheduling calendars. | 1.50 | Integration | Medium | 1.00 | 2.00 | Bi-directional leave sync active between Zoho People and Projects. | Zoho People organization access available. | Yes | No | Resource Capacity & Utilization Engine › Workload Leveling & Over-Allocation Mitigation | Requires
Zoho Projects | Advanced Timesheets, Multi-Tier Billing & Approvals | Staff/Role/Project hourly billing rates, mobile tracking, multi-tier approval chains, and payroll lock periods. | Multi-Tier Billing Rates & Approvals | Commercial rate card modeling and multi-stage financial approval chains. | Billing Rates & Governance Approval | Set up rate cards, mobile timers, and lockdown periods. | Multi-Tier Billing Rates Architecture | Configure Staff-Based, Role-Based, and Project-Based hourly billing rates for accurate client invoicing and costing. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Configured rate cards active across all billing roles. | Contractual billing rate schedule provided. | Yes | No | Time Tracking & Timesheet Logging › Daily & Weekly Timesheet Logging | Requires
Zoho Projects | Advanced Timesheets, Multi-Tier Billing & Approvals |  | Multi-Tier Billing Rates & Approvals |  | Billing Rates & Governance Approval |  | Live Stopwatch Timer & Mobile Tracking | Configure in-app live multi-timer stopwatch and mobile time tracking with automated background work logging. | 1.50 | Configuration | Low | 1.00 | 2.00 | Mobile time tracking verified with background work sync. | Mobile app access enabled. | No | No | Multi-Tier Billing Rates & Approvals › Multi-Tier Billing Rates Architecture | Requires
Zoho Projects | Advanced Timesheets, Multi-Tier Billing & Approvals |  | Multi-Tier Billing Rates & Approvals |  | Billing Rates & Governance Approval |  | Multi-Tier Timesheet Approval & Lock Periods | Establish multi-stage approval workflows (PM -> Finance Head) with automated timesheet lockdown at payroll cutoff. | 2.50 | Configuration | Medium | 2.00 | 3.00 | Automated payroll lock periods active preventing past edits. | Payroll cutoff cycle confirmed. | Yes | No | Multi-Tier Billing Rates & Approvals › Live Stopwatch Timer & Mobile Tracking | Requires
Zoho Projects | Issue / Bug SLA Management & Business Rules | Custom bug tracking layouts, SLA targets, automated business assignment rules, and escalation hierarchies. | Issue SLA & Business Automation Rules | Enforce strict contractual response and resolution SLAs with automated multi-tier escalations. | SLA Governance & Issue Automation | Set up custom bug layouts, SLA targets, and escalation triggers. | Custom Issue Layouts, Email-to-Issue & Views | Build custom bug tracking layouts, custom severity matrices, email-to-issue alias, and issue-to-task linking. | 2.00 | Customization | Medium | 1.50 | 2.50 | Custom issue tracking layout with inbound email parser. | Issue fields dictionary approved. | Yes | No | Issue & Bug Tracking Engine › Issue Logging & Classification Setup | Requires
Zoho Projects | Issue / Bug SLA Management & Business Rules |  | Issue SLA & Business Automation Rules |  | SLA Governance & Issue Automation |  | SLA Management & Business Rules Auto-Assign | Configure formal SLAs (First Response & Resolution) and automated business rules for auto-assignment and field updates. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Active SLA policies with automatic technician assignment. | Contractual SLA targets confirmed. | Yes | No | Issue SLA & Business Automation Rules › Custom Issue Layouts, Email-to-Issue & Views | Requires
Zoho Projects | Issue / Bug SLA Management & Business Rules |  | Issue SLA & Business Automation Rules |  | SLA Governance & Issue Automation |  | Multi-Level Escalation Automation Rules | Automate multi-tier escalation triggers routing SLA-breaching issues to senior leadership via high-priority alerts. | 1.50 | Configuration | Low | 1.00 | 2.00 | Multi-level escalation rules active on SLA breach. | Escalation recipients documented. | No | No | Issue SLA & Business Automation Rules › SLA Management & Business Rules Auto-Assign | Requires
Zoho Projects | Ecosystem Integrations: Zoho Books, CRM & Office | Direct Zoho Books timesheet-to-invoice sync, Zoho CRM Deal Won auto-provisioning, and MS 365 / Google Workspace sync. | Ecosystem Closed-Loop Integrations | Bridge sales pipeline handoff, back-office billing, and team collaboration into an automated pipeline. | Books, CRM & Office Cloud Interconnect | Connect Books timesheet invoicing, CRM deal templates, and Office suites. | Direct Zoho Books Timesheet-to-Invoice Sync | Configure bi-directional sync linking Zoho Projects with Zoho Books/Invoice for one-click invoice generation from approved hours. | 2.50 | Integration | High | 2.00 | 3.50 | 1-click client invoice generation operational from approved timesheets. | Zoho Books organization access and chart of accounts confirmed. | Yes | No | Multi-Tier Billing Rates & Approvals › Multi-Tier Timesheet Approval & Lock Periods | Requires
Zoho Projects | Ecosystem Integrations: Zoho Books, CRM & Office |  | Ecosystem Closed-Loop Integrations |  | Books, CRM & Office Cloud Interconnect |  | Zoho CRM Deal-to-Project Auto-Creation | Auto-instantiate project templates upon Deal Won in Zoho CRM, syncing client details, scope deliverables, and target dates. | 2.00 | Integration | Medium | 1.50 | 2.50 | Automated project provisioning verified upon CRM Deal Won trigger. | Zoho CRM deal stages and field mapping agreed. | Yes | No | Project Template & Delivery Standardization › Master Project Template Creation (Up to 5) | Requires
Zoho Projects | Ecosystem Integrations: Zoho Books, CRM & Office |  | Ecosystem Closed-Loop Integrations |  | Books, CRM & Office Cloud Interconnect |  | Google Workspace & Microsoft 365 Integration | Connect Google Drive/Calendar and Microsoft Teams/Outlook/OneDrive/SharePoint with CSV & MS Project (.mpp) migration. | 2.50 | Integration | Medium | 2.00 | 3.00 | MS 365 / Google Workspace sync active with document repository. | Cloud tenant admin credentials available. | Yes | No | Document Storage & Meeting Collaboration › Project Folder & Document Hierarchy | Requires
Zoho Projects | Departmental Training, Simulation & 30-Day Hypercare | Departmental role-based training workshops, 25+ real-data UAT scenario simulations, and dedicated 30-day post go-live hypercare. | Professional Change Management & Hypercare | Rigorous UAT validation and dedicated consultant support ensuring zero-defect go-live. | Training Sprints, UAT & Post-Go-Live Care | Deliver training academies, simulate UAT, and provide 30-day hypercare. | Departmental Training Sprints | Deliver specialized training workshops for Project Managers, Resource Planners, and Finance/Billing administrators. | 2.50 | Training | Medium | 2.00 | 3.00 | Completed training sprints for PMs, resource planners, and billing team. | All professional configuration modules validated. | Yes | No | Ecosystem Closed-Loop Integrations › Direct Zoho Books Timesheet-to-Invoice Sync | Requires
Zoho Projects | Departmental Training, Simulation & 30-Day Hypercare |  | Professional Change Management & Hypercare |  | Training Sprints, UAT & Post-Go-Live Care |  | User Acceptance Testing (UAT) Simulation | Simulate 25+ real client delivery scenarios: scope changes, baseline shifts, contractor timesheets, and invoice sync. | 2.00 | Validation | Medium | 1.50 | 2.50 | Formal signed UAT sign-off document with zero open defects. | UAT test cases and client test team available. | Yes | No | Professional Change Management & Hypercare › Departmental Training Sprints | Requires
Zoho Projects | Departmental Training, Simulation & 30-Day Hypercare |  | Professional Change Management & Hypercare |  | Training Sprints, UAT & Post-Go-Live Care |  | 30-Day Post Go-Live Hypercare | Dedicated consultant on-call support during first monthly project closing, client billing run, and resource reviews. | 1.50 | Support | Low | 1.00 | 2.00 | Completed 30-day hypercare period with monthly project closing report. | Production cutover executed. | Yes | No | Professional Change Management & Hypercare › User Acceptance Testing (UAT) Simulation | Requires
--- LAYER: ELITE IMPLEMENTATION TASKS ---
Zoho Projects | Critical Path Method (CPM), Schedule Risk & Baseline Engine | Enterprise CPM optimization, zero-slack bottlenecks, unlimited baseline comparison engine, and automated schedule risk alerts. | Enterprise CPM & Baseline Governance | Mathematical critical path optimization and multi-version baseline comparison across complex programs. | CPM Optimization & Baseline Versioning | Configure CPM calculation, baseline versions, and buffer management. | Critical Path Method (CPM) Optimization | Identify true critical path deliverables, zero-slack tasks, and automated schedule compression options. | 3.00 | Configuration | High | 2.50 | 4.00 | Dynamic CPM calculation active highlighting zero-slack deliverable paths. | Complex WBS dependencies established. | No | No | Critical Path (CPM) & Baseline Variance › Advanced Gantt Configuration & Critical Path | Requires
Zoho Projects | Critical Path Method (CPM), Schedule Risk & Baseline Engine |  | Enterprise CPM & Baseline Governance |  | CPM Optimization & Baseline Versioning |  | Multi-Version Baseline Comparison Engine | Maintain unlimited baseline versions (Original Contract, Approved Scope Change, Revised Schedule) with variance tracking. | 3.00 | Configuration | Medium | 2.50 | 3.50 | Multi-version baseline comparison active with visual variance overlays. | Baseline versioning criteria confirmed. | Yes | No | Enterprise CPM & Baseline Governance › Critical Path Method (CPM) Optimization | Requires
Zoho Projects | Critical Path Method (CPM), Schedule Risk & Baseline Engine |  | Enterprise CPM & Baseline Governance |  | CPM Optimization & Baseline Versioning |  | Schedule Variance & Buffer Management | Automate slack time tracking, schedule performance index warnings, and delay alerts for program managers. | 2.50 | Configuration | Medium | 2.00 | 3.00 | Automated slack buffer threshold alerts operational. | Schedule risk thresholds defined. | No | No | Enterprise CPM & Baseline Governance › Multi-Version Baseline Comparison Engine | Requires
Zoho Projects | Multi-Project Resource Forecasting & Capacity Balancing | Cross-project capacity forecasting 3 to 6 months in advance, multi-project resource balancing, and labor margin yield analytics. | Enterprise Resource Forecasting & Margin Analytics | Long-term capacity forecasting and real-time labor yield margin tracking. | Resource Capacity Forecasting & Yield Optimization | Build 3-6 month forecasting views, balancing rules, and labor margin yield analytics. | Multi-Project Resource Capacity Forecasting | Forecast team and department capacity requirements 3 to 6 months in advance based on active and pipeline project commitments. | 3.50 | Configuration | High | 3.00 | 4.50 | Forward-looking 6-month capacity forecast model operational. | Pipeline resource demand profiles agreed. | Yes | No | Resource Capacity & Utilization Engine › Resource Allocation & Heatmap Setup | Requires
Zoho Projects | Multi-Project Resource Forecasting & Capacity Balancing |  | Enterprise Resource Forecasting & Margin Analytics |  | Resource Capacity Forecasting & Yield Optimization |  | Multi-Project Resource Balancing & Allocation Rules | Configure cross-project resource utilization views and daily/weekly capacity allocation limits to eliminate multi-project over-commitment. | 3.00 | Configuration | Medium | 2.50 | 3.50 | Multi-project balancing rules active preventing dual-booking. | Cross-project allocation priorities set. | No | No | Enterprise Resource Forecasting & Margin Analytics › Multi-Project Resource Capacity Forecasting | Requires
Zoho Projects | Multi-Project Resource Forecasting & Capacity Balancing |  | Enterprise Resource Forecasting & Margin Analytics |  | Resource Capacity Forecasting & Yield Optimization |  | Resource Cost vs. Billing Margin Yield Analytics | Compare staff cost rates against client billing rates to analyze real-time gross margin and labor yield per team member and department. | 3.00 | Configuration | High | 2.50 | 3.50 | Labor margin yield analytics view operational. | Internal cost rate cards and external billing rates provided. | Yes | No | Enterprise Resource Forecasting & Margin Analytics › Multi-Project Resource Balancing & Allocation Rules | Requires
Zoho Projects | Enterprise Project Budgeting & EVM Financial Flow | Hierarchical amount/hour budgets, live cost burn tracking, automated threshold escalations, hard-stop budget freezes, and Earned Value Management (EVM). | Enterprise Project Budgeting & EVM Flow | Closed-loop financial governance protecting project gross margins against budget overruns. | Budget Architecture & EVM Controls | Configure hierarchical budgets, real-time cost burn, Deluge hard freeze, and EVM formulas. | Multi-Tier Budget Architecture & Baseline Allocation | Setup hierarchical project-level, milestone-level, and task-level budgeting in amount and hours with baseline cost cards and profit margin models. | 3.50 | Configuration | High | 3.00 | 4.50 | Hierarchical multi-tier budget structure active across active projects. | Project budget allocation models approved. | Yes | No | Multi-Tier Billing Rates & Approvals › Multi-Tier Billing Rates Architecture | Requires
Zoho Projects | Enterprise Project Budgeting & EVM Financial Flow |  | Enterprise Project Budgeting & EVM Flow |  | Budget Architecture & EVM Controls |  | Real-Time Cost Burn, Expense Ingestion & Margin Tracking | Automate live ingestion of staff timesheet costs and categorized project expenses (direct, subcontractor, overhead) to compute live gross margin burn. | 3.50 | Configuration | High | 3.00 | 4.50 | Live gross margin burn engine calculating actual cost in real time. | Direct and overhead expense categories mapped. | Yes | No | Enterprise Project Budgeting & EVM Flow › Multi-Tier Budget Architecture & Baseline Allocation | Requires
Zoho Projects | Enterprise Project Budgeting & EVM Financial Flow |  | Enterprise Project Budgeting & EVM Flow |  | Budget Architecture & EVM Controls |  | Automated Budget Threshold Escalations & Hard-Stop Freeze | Configure automated multi-tier alert triggers (50%, 80%, 100%) and Deluge/Blueprint hard-stop validation locks halting unapproved work logs upon budget breach. | 3.00 | Customization | High | 2.50 | 4.00 | Deluge hard-stop freeze operational, blocking work logging upon 100% budget breach. | Budget breach escalation protocol approved. | Yes | Yes | Enterprise Project Budgeting & EVM Flow › Real-Time Cost Burn, Expense Ingestion & Margin Tracking | Requires
Zoho Projects | Enterprise Project Budgeting & EVM Financial Flow |  | Enterprise Project Budgeting & EVM Flow |  | Budget Architecture & EVM Controls |  | Earned Value Management (EVM) & Revenue Realization Flow | Configure Planned Value (PV), Earned Value (EV), Actual Cost (AC), CPI, SPI, EAC, and link milestone deliverables to revenue realization in Zoho Books. | 3.00 | Configuration | High | 2.50 | 4.00 | EVM metric calculations (CPI/SPI/EAC) live with Books revenue realization sync. | Financial recognition rules approved. | Yes | No | Enterprise Project Budgeting & EVM Flow › Automated Budget Threshold Escalations & Hard-Stop Freeze | Requires
Zoho Projects | Custom Modules Architecture & Enterprise Issue Governance | Dedicated custom data entities (Change Requests, Submittals, RFIs), multi-channel bug ingestion, and strict contractual SLA penalty tracking. | Custom Modules & Issue SLA Governance | Extend data architecture for non-standard governance entities with contractual SLA penalties. | Custom Modules & Contractual SLA Management | Build Change Request custom modules, webhook ingestion, and penalty SLA rules. | Custom Modules Setup (Change Requests & Non-Standard Entities) | Build dedicated custom data entities within Zoho Projects (e.g., Change Requests, Submittals, RFI) with custom layouts and relational links. | 3.00 | Customization | High | 2.50 | 4.00 | Custom modules active with relational links to projects and milestones. | Custom entity data specifications provided. | Yes | No | Custom Data Architecture & Dynamic Layouts › Custom Project & Task Field Architecture | Requires
Zoho Projects | Custom Modules Architecture & Enterprise Issue Governance |  | Custom Modules & Issue SLA Governance |  | Custom Modules & Contractual SLA Management |  | Multi-Channel Issue / Bug Ingestion & Webhooks | Capture issues and defects via web forms, customer portals, email-to-issue parsers, and external QA webhook pipelines. | 3.00 | Integration | Medium | 2.50 | 3.50 | Inbound QA webhook endpoints and multi-channel intake pipelines verified. | External QA systems identified. | Yes | Yes | Custom Modules & Issue SLA Governance › Custom Modules Setup (Change Requests & Non-Standard Entities) | Requires
Zoho Projects | Custom Modules Architecture & Enterprise Issue Governance |  | Custom Modules & Issue SLA Governance |  | Custom Modules & Contractual SLA Management |  | Multi-Tier Escalation Hierarchies & Penalty SLA Tracking | Automate strict contractual SLA breach notifications to executives and client representatives with penalty calculation flags. | 2.50 | Configuration | Medium | 2.00 | 3.00 | Contractual SLA breach penalty tracking and C-suite alert triggers operational. | Contractual SLA penalty terms confirmed. | Yes | No | Custom Modules & Issue SLA Governance › Multi-Channel Issue / Bug Ingestion & Webhooks | Requires
Zoho Projects | Multi-Stakeholder Client & Subcontractor Sandboxed Portals | Segmented external portal environments, subcontractor task work logging, and formal change order digital approval workflows. | Multi-Stakeholder Sandboxed Portals | Secure, segmented portal architecture for external clients, subcontractors, and vendors. | External Portal Architecture & Sandboxing | Configure client and vendor sandboxes with digital change order sign-offs. | Multi-Tier External Portal Architecture | Configure segmented, secure portal environments for enterprise clients, subcontractors, and freelance specialists. | 3.00 | Security | High | 2.50 | 4.00 | Multi-stakeholder external portal environments configured with restricted security. | External access policies approved. | Yes | No | Granular Profile & Permission Matrix › Client User Setup & External Permissions | Requires
Zoho Projects | Multi-Stakeholder Client & Subcontractor Sandboxed Portals |  | Multi-Stakeholder Sandboxed Portals |  | External Portal Architecture & Sandboxing |  | Subcontractor Task Assignment & Work Logging | Enable external contractors to log task progress and billable hours within restricted project sandboxes without visibility to full scope. | 2.50 | Configuration | Medium | 2.00 | 3.00 | Subcontractor sandbox access operational with blind internal commercial data. | Contractor work scope defined. | No | No | Multi-Stakeholder Sandboxed Portals › Multi-Tier External Portal Architecture | Requires
Zoho Projects | Multi-Stakeholder Client & Subcontractor Sandboxed Portals |  | Multi-Stakeholder Sandboxed Portals |  | External Portal Architecture & Sandboxing |  | Client Deliverable Sign-Off & Change Order Approval | Build formal change order request workflows requiring client digital approval before scope, budget, or timeline adjustments. | 2.50 | Customization | Medium | 2.00 | 3.00 | Digital change order sign-off workflow active in client portal. | Client approval authority matrix provided. | Yes | No | Multi-Stakeholder Sandboxed Portals › Subcontractor Task Assignment & Work Logging | Requires
Zoho Projects | Client Collaboration Portal, Pages (Wiki) & Forums | Branded client self-service portal, deliverable milestone approval workflows, and interactive project documentation Wikis. | Client Collaboration & Knowledge Wikis | Transparent client engagement and standardized interactive project documentation. | Client Self-Service & Wiki Governance | Set up client self-service, milestone sign-offs, and project Wikis. | Branded Client Self-Service Portal | Configure secure client portal access with restricted visibility limited exclusively to designated tasks and milestones. | 2.00 | Configuration | Medium | 1.50 | 2.50 | Branded client self-service portal active with custom branding. | Client branding assets provided. | Yes | No | Multi-Stakeholder Sandboxed Portals › Multi-Tier External Portal Architecture | Requires
Zoho Projects | Client Collaboration Portal, Pages (Wiki) & Forums |  | Client Collaboration & Knowledge Wikis |  | Client Self-Service & Wiki Governance |  | Client Deliverable Approval Workflows | Enable external client stakeholders to review completed deliverables, approve milestones, or request revisions directly. | 1.50 | Configuration | Medium | 1.00 | 2.00 | Client review and milestone approval state active. | Deliverable acceptance criteria confirmed. | Yes | No | Client Collaboration & Knowledge Wikis › Branded Client Self-Service Portal | Requires
Zoho Projects | Client Collaboration Portal, Pages (Wiki) & Forums |  | Client Collaboration & Knowledge Wikis |  | Client Self-Service & Wiki Governance |  | Interactive Forums, Pages (Wiki) & Docs | Setup project discussion forums, announcement boards, and interactive Wiki pages for standardized project documentation. | 1.50 | Configuration | Low | 1.00 | 2.00 | Project Wiki templates and discussion forums active. | Documentation templates provided. | No | No | Client Collaboration & Knowledge Wikis › Client Deliverable Approval Workflows | Requires
Zoho Projects | Zoho Ecosystem Deep Interconnect (Desk, People, Sprints) | Bi-directional Zoho Desk ticket-to-task sync, Zoho People leave/shifts sync, and Zoho Sprints hybrid agile synchronization. | Zoho Ecosystem Deep Interconnect | Unified cross-application handoffs connecting customer support, agile sprints, and HR calendars. | Desk, People & Sprints Tri-Directional Sync | Configure Desk ticket sync, People leave/shifts, and Sprints integration. | Zoho Desk Ticket-to-Task / Bug Interconnect | Bi-directional sync converting customer support tickets into project tasks or bugs with live status reflection. | 3.50 | Integration | High | 3.00 | 4.50 | Bi-directional ticket-to-task sync operational with live status reflection. | Zoho Desk department access available. | Yes | No | Issue & Bug Tracking Engine › Issue Logging & Classification Setup | Requires
Zoho Projects | Zoho Ecosystem Deep Interconnect (Desk, People, Sprints) |  | Zoho Ecosystem Deep Interconnect |  | Desk, People & Sprints Tri-Directional Sync |  | Zoho People Employee Leaves & Resource Calendar Sync | Live two-way sync of employee leave approvals, shifts, and public holidays into project timelines. | 3.50 | Integration | Medium | 3.00 | 4.00 | Two-way employee leave and shift sync active across all projects. | Zoho People integration permissions enabled. | Yes | No | Resource Capacity & Utilization Engine › Zoho People Leave Integration & Shift Sync | Requires
Zoho Projects | Zoho Ecosystem Deep Interconnect (Desk, People, Sprints) |  | Zoho Ecosystem Deep Interconnect |  | Desk, People & Sprints Tri-Directional Sync |  | Zoho Sprints & Cliq Interactive Channels | Configure hybrid agile sprint syncing with Zoho Sprints and auto-create dedicated Cliq project channels and standups. | 3.00 | Integration | Medium | 2.50 | 3.50 | Hybrid agile sprint sync and automated Cliq project bot operational. | Zoho Sprints & Cliq access available. | Yes | No | Zoho Ecosystem Deep Interconnect › Zoho People Employee Leaves & Resource Calendar Sync | Requires
Zoho Projects | Custom Deluge Scripting & Enterprise Workflow Functions | Complex serverless Deluge functions, automated parent task completion, dynamic deadline recalculation, and notification bots. | Serverless Deluge Automation Engine | Custom business logic development executing dynamic project computations and portfolio notifications. | Deluge Scripts & Advanced Business Logic | Develop custom rollups, cross-module validation, and executive bots. | Complex Deluge Business Logic Development | Develop custom Deluge functions for automated parent task completion, dynamic deadline recalculation, and custom rollups. | 5.50 | Customization | High | 4.50 | 7.00 | Custom Deluge functions deployed and executing upon task update triggers. | Custom calculation logic signed off. | Yes | Yes | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Custom Deluge Scripting & Enterprise Workflow Functions |  | Serverless Deluge Automation Engine |  | Deluge Scripts & Advanced Business Logic |  | Cross-Module Data Validation & Auto-Trigger Scripts | Script cross-module data validation rules, automatic milestone unlocks, and project state change triggers. | 4.50 | Customization | High | 3.50 | 6.00 | Automated milestone unlock scripts and cross-module validation operational. | Validation rules documented. | No | Yes | Serverless Deluge Automation Engine › Complex Deluge Business Logic Development | Requires
Zoho Projects | Custom Deluge Scripting & Enterprise Workflow Functions |  | Serverless Deluge Automation Engine |  | Deluge Scripts & Advanced Business Logic |  | Custom Notification Bots & Automated Executive Summaries | Build automated Deluge bots sending weekly Slack/Cliq/Email portfolio summaries and risk digests. | 4.00 | Customization | Medium | 3.00 | 5.00 | Weekly automated portfolio digest bot active in Cliq / Slack. | Summary report KPI parameters defined. | Yes | Yes | Serverless Deluge Automation Engine › Cross-Module Data Validation & Auto-Trigger Scripts | Requires
Zoho Projects | Webhooks, REST APIs & DevOps Integrations | GitHub/GitLab/Bitbucket commit syncing, outbound ERP webhooks, and custom REST API endpoints for external data warehouses. | DevOps & Enterprise API Middleware | Bi-directional code repository tracking and real-time ERP event streaming. | Git Integration & Outbound Webhooks | Connect code commits, outbound event streaming, and custom REST APIs. | GitHub, GitLab & Bitbucket DevOps Integrations | Link code commits, pull requests, and git branches directly to Zoho Projects task IDs with auto-status updates. | 4.00 | Integration | High | 3.00 | 5.00 | Git commit linking operational with automatic task status transitions. | GitHub/GitLab repository admin access. | Yes | Yes | Work Breakdown Structure (WBS) Engine › Task & Nested Subtask Hierarchy | Requires
Zoho Projects | Webhooks, REST APIs & DevOps Integrations |  | DevOps & Enterprise API Middleware |  | Git Integration & Outbound Webhooks |  | Outbound Webhooks & ERP Real-Time Event Streaming | Configure real-time event webhooks pushing project status, milestones, and timesheets to enterprise ERP systems. | 4.00 | Integration | High | 3.00 | 5.00 | Real-time outbound webhooks firing payload to external ERP endpoint. | Target ERP API documentation provided. | Yes | Yes | DevOps & Enterprise API Middleware › GitHub, GitLab & Bitbucket DevOps Integrations | Requires
Zoho Projects | Webhooks, REST APIs & DevOps Integrations |  | DevOps & Enterprise API Middleware |  | Git Integration & Outbound Webhooks |  | Custom REST API Endpoints & Data Connectors | Develop custom API integrations for third-party billing, procurement, or legacy data warehouses. | 3.50 | Integration | High | 2.50 | 4.50 | Custom REST API connector verified with sample data payload. | External data schema confirmed. | Yes | Yes | DevOps & Enterprise API Middleware › Outbound Webhooks & ERP Real-Time Event Streaming | Requires
Zoho Projects | Zoho Analytics Executive BI & Portfolio Dashboards | Zoho Analytics relational data modeling, executive portfolio health BI dashboards, and scheduled C-suite KPI digests. | Zoho Analytics Executive BI Engine | Advanced data warehousing and interactive portfolio profitability intelligence for C-suite. | BI Modeling & Executive Dashboards | Deep sync data modeling, profitability dashboards, and automated C-suite digests. | Zoho Analytics Deep Sync & Data Modeling | Connect Zoho Projects database to Zoho Analytics with custom relational data tables and query tables. | 4.00 | Integration | High | 3.00 | 5.00 | Automated data sync established with relational data model in Analytics. | Zoho Analytics enterprise workspace available. | Yes | No | Timesheet Configuration & Work Logging › Standard Timesheet Approval Flow | Requires
Zoho Projects | Zoho Analytics Executive BI & Portfolio Dashboards |  | Zoho Analytics Executive BI Engine |  | BI Modeling & Executive Dashboards |  | Executive Portfolio Health & Margin Dashboards | Build interactive BI dashboards showing portfolio health, project profitability, burn rates, and team utilization. | 3.50 | Customization | High | 2.50 | 4.50 | Interactive executive BI dashboard active with live portfolio drill-downs. | Executive KPI report layouts agreed. | Yes | No | Zoho Analytics Executive BI Engine › Zoho Analytics Deep Sync & Data Modeling | Requires
Zoho Projects | Zoho Analytics Executive BI & Portfolio Dashboards |  | Zoho Analytics Executive BI Engine |  | BI Modeling & Executive Dashboards |  | Scheduled C-Suite Reports & KPI Alert Automations | Configure automated PDF/email KPI digests for CEO, PMO Director, and Finance Controller with anomaly alerts. | 3.00 | Configuration | Medium | 2.00 | 3.50 | Scheduled weekly KPI digests active with automated email dispatches. | Executive distribution list provided. | No | No | Zoho Analytics Executive BI Engine › Executive Portfolio Health & Margin Dashboards | Requires
Zoho Projects | Enterprise Change Management, UAT & 45-Day Hypercare | Multi-tier PMO training academy, 50+ enterprise UAT scenario simulations, and dedicated 45-day Senior Architect hypercare. | Enterprise Change Management & Hypercare | Comprehensive organizational adoption, full UAT simulation, and extended post go-live support. | PMO Academy, Enterprise UAT & 45-Day Care | Conduct PMO academy, 50+ scenario UAT, and 45-day hypercare support. | Multi-Tier PMO & Team Training Academy | Conduct tailored interactive training academies for PMO leads, Project Managers, and Technical Engineers with recorded video SOPs. | 5.50 | Training | High | 4.50 | 7.00 | Completed PMO and engineering training academy with video recordings. | Enterprise configuration completed. | Yes | No | Zoho Analytics Executive BI Engine › Executive Portfolio Health & Margin Dashboards | Requires
Zoho Projects | Enterprise Change Management, UAT & 45-Day Hypercare |  | Enterprise Change Management & Hypercare |  | PMO Academy, Enterprise UAT & 45-Day Care |  | 50+ Scenario End-to-End UAT Simulation | Rigorous simulation covering scope changes, critical path delays, subcontractor billing, and CRM cutover with real enterprise data. | 4.50 | Validation | High | 3.50 | 6.00 | Formal signed 50+ scenario UAT completion sign-off document. | UAT simulation dataset provided. | Yes | No | Enterprise Change Management & Hypercare › Multi-Tier PMO & Team Training Academy | Requires
Zoho Projects | Enterprise Change Management, UAT & 45-Day Hypercare |  | Enterprise Change Management & Hypercare |  | PMO Academy, Enterprise UAT & 45-Day Care |  | 45-Day Enterprise Hypercare & Post Go-Live Audit | Dedicated Senior Solution Architect on-call for two full billing cycles, project kickoffs, and PMO optimization reviews. | 6.50 | Support | Medium | 5.00 | 8.00 | Completed 45-day hypercare period and final PMO optimization audit report. | Enterprise production cutover executed. | Yes | No | Enterprise Change Management & Hypercare › 50+ Scenario End-to-End UAT Simulation | Requires
TOTAL ESTIMATED IMPLEMENTATION EFFORT: | [8 empty] | 204.00 Hours