## Overview _ Hours Summary
ELITE TECH CORPORATION
Zoho Projects Implementation — Master Scope & Hours Overview
Executive comparison of implementation packages, module breakdown, activity counts, and estimated consulting effort.
1. EXECUTIVE PACKAGE COMPARISON & ESTIMATED EFFORT
Implementation Package | Target Timeline | Included Modules | Implementation Activities | Total Estimated Hours | Recommended Target Profile
Basic Package | 7–10 Working Days | 10 Modules | 28 Activities | 26.0 Hours | Early-stage teams, creative agencies & startups needing structured task tracking, milestones, basic timesheets, Zoho Meeting/Mail setup & standard project templates.
Professional Package | 15–20 Working Days | 11 Modules | 33 Activities | 63.0 Hours | Growing mid-market enterprises, IT services & engineering firms requiring custom layouts, stage-gate Blueprints, resource capacity leveling, timesheet approvals, Zoho Books/CRM/People sync, MS 365/Google Workspace & MPP migration.
Elite Package | 30–45 Working Days | 11 Modules | 34 Activities | 115.0 Hours | High-growth enterprises, EPC/construction corporations, software engineering departments & PMOs requiring multi-entity governance, end-to-end Project Budgeting Flow, EVM, Client & Subcontractor Portals & Wikis, custom Deluge scripts, Zoho Desk/Analytics/Sprints sync & extended hypercare.
2. ESTIMATED CONSULTING HOURS BREAKDOWN BY STAGE
Stage | Implementation Stage & Functional Focus | Basic Hours | Pro Hours | Elite Hours | Stage Deliverables & Verification
Stage 1 | Workspace Architecture, Custom Domain & Security | 7.0h | 9.0h | — | Portal profile, work calendar, custom domain mapping, SSO/SAML, custom profiles, user groups, and sandbox security.
Stage 2 | Master Templates, WBS & Legacy Migration | 5.5h | 5.5h | — | Repeatable template library (up to 20+), WBS hierarchy, milestones, and Jira/Basecamp/Monday/MPP migration cutover.
Stage 3 | Custom Fields, Layouts, Dynamic Rules & Web Tabs | — | 6.0h | — | Custom fields across modules, dynamic layout visibility rules, custom web tabs, and custom status workflows.
Stage 4 | Milestone & Task Blueprints (Process Governance) | — | 7.0h | — | Visual state machine Blueprints, mandatory field validations, stage-gate deliverable sign-offs, and automated trigger actions.
Stage 5 | Gantt Scheduling, Critical Path (CPM) & Baseline Variance | 2.5h | 5.5h | 8.5h | Interactive chronological Gantt charts, FS/SS/FF/SF dependencies, multi-version baselines, and CPM schedule risk optimization.
Stage 6 | Resource Capacity Planning & Workload Balancing | — | 5.5h | 9.5h | Resource allocation heatmap, weekly capacity limits, multi-project resource balancing view, and Zoho People leave/shift sync.
Stage 7 | Timesheets, Work Logging & Multi-Tier Billing Rates | 2.5h | 6.0h | — | Live stopwatch timer, task work logging, staff/role/project billing rates, and multi-tier manager timesheet approvals.
Stage 8 | Enterprise Project Budgeting & EVM Financial Flow | — | — | 13.0h | Exclusive to Elite: multi-tier baselines, cost vs billing rates, live cost burn tracking, threshold alerts, hard budget freeze, and EVM (CPI/SPI).
Stage 9 | Client & Subcontractor Portals, Wikis & Docs | 2.5h | — | 13.0h | Branded client self-service portal, subcontractor restricted sandboxes, deliverable sign-offs, file repository, and Pages/Wiki forums.
Stage 10 | Custom Modules & Issue SLA Governance | 2.0h | 5.5h | 8.5h | Custom modules (Change Requests/Submittals), custom issue fields, email alias, SLA resolution policies, and multi-tier escalations.
Stage 11 | Ecosystem Integrations (Zoho Books, CRM, Desk, Office) | — | 7.0h | 10.0h | Direct Zoho Books timesheet-to-invoice sync, Zoho CRM Deal-to-Project auto-creation, Zoho Desk tickets, Zoho Sprints, and MS 365/Google sync.
Stage 12 | Custom Deluge Scripting, Webhooks & DevOps APIs | — | — | 25.5h | Custom Deluge scripts for auto-calculations, GitHub/GitLab commit linking, outbound webhooks, and REST API integration.
Stage 13 | Executive BI Analytics, Training Academy & Hypercare | 4.0h | 6.0h | 27.0h | Zoho Analytics executive BI portfolio dashboards, multi-tier training academy, 50+ UAT scenario simulation & dedicated 45-day hypercare.
| TOTAL ESTIMATED IMPLEMENTATION EFFORT: | 26.0 Hours | 63.0 Hours | 115.0 Hours | Full Turnkey Implementation + Training & Hypercare Included

## Basic Package
ELITE TECH CORPORATION
Zoho Projects Implementation — Basic Package
Scope Summary: 10 Modules ¦ 28 Activities ¦ Total Estimated Effort: 26.0 Hours ¦ Target Timeline: 7–10 Working Days Foundational project workspace setup covering company portal, user permissions, standardized WBS templates, Gantt charts, timesheets, and team onboarding.
Sno | Module | Activities | Description | Est. Hours
1 | Organization & Portal Setup | Portal Profile & Branding | Configure company portal name, official URL domain, company logo, color theme, and favicon for brand identity. | 1.0 hrs
|  | Work Calendar, Timezone & Operating Hours | Setup company working days, official business hours, regional timezone, date format, default currency, and 1 holiday calendar. | 1.0 hrs
|  | Default Notification Preferences & Email Setup | Configure system notification email sender, SPF/DKIM verification, instant vs daily digest alert frequencies, and feed updates. | 0.5 hrs
2 | User Roles & Access Permissions | User Profiles & Standard Role Matrix | Setup default role hierarchies (Admin, Project Manager, Team Member, Client User) with defined baseline access. | 1.0 hrs
|  | User Onboarding & Profile Verification | Add and invite initial organization users (up to 10 users), configure profile details, user groups, and verify invitation acceptance. | 1.0 hrs
|  | Data Access & Security Boundaries | Configure baseline security restrictions to prevent unauthorized task deletion, private project access, and data export. | 0.5 hrs
3 | Project Structure & Grouping | Project Groups & Master Tag Library | Establish structured project groups by department/client and setup standard master tag library with restricted admin-only tag creation. | 1.0 hrs
|  | Client Association & Tags | Configure client master association, industry tagging, and active/archive project state settings. | 1.0 hrs
4 | Standard Project Template Architecture | Master Project Template Creation (Up to 5) | Design up to 5 standard reusable project templates equipped with standardized milestones, task lists, and recurring checklists. | 1.5 hrs
|  | Task List Standardization & Plain/Kanban Views | Configure standard functional task groupings (Initiation, Execution, QA, Handover) with Classic list, Kanban, and Calendar views. | 1.0 hrs
|  | Template Cloning & Instantiation | Test and validate rapid project generation via one-click template cloning with date offset calculations. | 0.5 hrs
5 | Task Breakdown Structure (WBS) & Milestones | Milestone & Phase Configuration | Configure project milestones, delivery target dates, internal/external flags, and milestone owners. | 1.0 hrs
|  | Task & Nested Subtask Hierarchy | Build multi-level task breakdown structure (WBS) with parent tasks, subtasks, descriptions, assignees, and bulk update actions. | 1.0 hrs
|  | Task Priority, Tags & Recurrence | Set task priority levels (Low, Medium, High, Urgent), custom organizational tags, and recurring task schedules. | 0.5 hrs
6 | Task Dependencies & Gantt Visualization | Finish-to-Start (FS) Dependencies | Establish sequential Finish-to-Start links between prerequisite tasks and successor deliverables. | 1.0 hrs
|  | Chronological Gantt Chart View & Export | Configure standard Gantt chart interface with milestone markers, progress percentages, dependency lines, and PDF/XLS export. | 1.0 hrs
|  | Schedule Cascading Verification | Test and verify automatic schedule date shifts when predecessor tasks experience delivery delays. | 0.5 hrs
7 | Timesheets & Work Logging | Daily & Weekly Timesheet Logging | Setup manual time entry grid allowing team members to record daily task work hours and task progress comments. | 1.0 hrs
|  | Live Stopwatch Timer & Billable Classification | Configure in-app live stopwatch timer and billable/non-billable status toggles across tasks and time logs. | 0.5 hrs
|  | Standard Timesheet Approval Flow | Configure single-tier Project Manager approval workflow for weekly team timesheet submissions. | 1.0 hrs
8 | Documents, Zoho Meeting & File Repository | Project Folder & Document Hierarchy | Configure standardized document folders aligned with project milestones and execution phases. | 1.0 hrs
|  | File Uploads, Previews & Version History | Enable document attachments, inline preview capabilities, and file version control for deliverables and specs. | 1.0 hrs
|  | Zoho Meeting & Zoho Mail Alias Setup | Configure embedded in-task Zoho Meeting scheduling and inbound Zoho Mail aliases for direct task email threads. | 0.5 hrs
9 | Basic Issue / Bug Tracking | Issue Logging & Classification Setup | Configure standard issue tracking module with severity, priority, bug classification, and reproduction steps. | 1.0 hrs
|  | Standard Issue Lifecycle States & Workflow | Setup standard bug resolution status path: Open -> In Progress -> Under Review -> Resolved -> Closed. | 1.0 hrs
10 | Team Training, Walkthrough & SOPs | Project Manager Hands-On Training | Interactive coaching session for PMs covering project creation, Gantt scheduling, task assignment, and timesheets. | 1.5 hrs
|  | Team Member Task & Time Tracking Training | Practical virtual workshop guiding end users on task status updates, timesheet submissions, and collaboration. | 1.5 hrs
|  | Standard Operating Procedure (SOP) Quick Guide | Deliver comprehensive PDF user guide detailing day-to-day project workflows, conventions, and FAQs. | 1.0 hrs
TOTAL ESTIMATED IMPLEMENTATION EFFORT: |  |  |  | 26.0 Hours

## Professional Package
ELITE TECH CORPORATION
Zoho Projects Implementation — Professional Package
Scope Summary: 11 Modules ¦ 33 Activities ¦ Total Estimated Effort: 63.0 Hours ¦ Target Timeline: 15–20 Working Days End-to-end project operations with custom layouts, stage-gate Blueprints, resource capacity leveling, timesheet billing rates, and Zoho Books/CRM integration.
Sno | Module | Activities | Description | Est. Hours
1 | Multi-Department Workspace & Custom Domain | Multi-Department Portfolio Structure | Configure multi-department project groups, division portfolios, and client account hierarchies for clear organization navigation. | 2.0 hrs
|  | Custom Domain Mapping & Portal URL Branding | Map corporate domain (e.g., projects.company.com) to the portal URL, removing default Zoho subdomains. | 1.5 hrs
|  | Multi-Regional Holiday Calendars | Setup up to 3 regional and national holiday calendars linked to task due dates, avoiding weekend and holiday false alerts. | 1.0 hrs
2 | Granular Roles, Profiles & Field Security | Granular Custom Role & Designation Matrices | Create tailored role matrices for Project Directors, Technical Leads, Billing Admins, and Client Users with module-level access. | 2.0 hrs
|  | Client User Setup & External Permissions | Configure secure external client user access with strict view/edit permissions restricted exclusively to assigned projects. | 1.5 hrs
|  | Confidential Project Security & Field Masking | Implement restricted data boundaries hiding internal notes, billing rates, and private discussions from unauthorized staff. | 1.0 hrs
3 | Multi-Template Library & Dependency Logic | Extended Project Template Library (Up to 20+) | Build up to 20+ specialized templates for Agile, Waterfall, Retainer, and Client Onboarding with automated recurring tasks. | 2.5 hrs
|  | Advanced Dependency Architecture (FS, SS, FF, SF) | Configure complete dependency matrix covering Start-to-Start, Finish-to-Finish, and Start-to-Finish task dependencies. | 1.5 hrs
|  | Strict Project Scheduling & Auto-Rescheduling | Configure strict dependency enforcement where shifting predecessor completion dates automatically re-schedules successor tasks. | 1.5 hrs
4 | Task Breakdown Structure (WBS), Views & Dynamic Layouts | Custom Project & Task Field Architecture | Design custom picklists, formula fields, date triggers, and external reference numbers across project, task & issue modules. | 2.5 hrs
|  | Dynamic Layout Rules & Conditional Visibility | Configure layout rules that dynamically show or hide fields based on task category, department, or project stage. | 2.0 hrs
|  | Custom Status Workflows & Custom Web Tabs | Design multi-stage status paths (Backlog -> Scoping -> In Dev -> QA -> UAT -> Deployed) and embed external web tabs. | 1.5 hrs
5 | Milestone & Task Blueprints (Process Governance) | Task Status Blueprint Design | Build strict visual state machine Blueprints requiring mandatory checklist completion and field data before status transitions. | 3.0 hrs
|  | Milestone Gatekeeping & Deliverable Sign-Offs | Enforce rigorous stage-gate approval Blueprints preventing milestone closure without uploaded deliverables and manager sign-off. | 2.0 hrs
|  | Automated Blueprint Actions, Macros & Alerts | Trigger automated task updates, macro executions, ownership reassignments, and stakeholder email alerts during transitions. | 2.0 hrs
6 | Interactive Gantt Scheduling & Project Baselines | Advanced Gantt Configuration & Critical Path | Setup interactive Gantt chart with automated Critical Path Method (CPM) calculation identifying bottleneck deliverables. | 2.0 hrs
|  | Project Baseline Tracking & Variance Analysis | Capture project baseline snapshots and compare original planned schedules against actual execution timelines. | 2.0 hrs
|  | Multi-Project Portfolio Gantt View | Configure cross-project chronological timeline tracking to monitor multiple active client projects on a single canvas. | 1.5 hrs
7 | Resource Capacity Planning & Workload Balancing | Resource Allocation & Heatmap Setup | Configure resource utilization charts to visualize team workload distribution based on allocated hours vs capacity. | 2.0 hrs
|  | Workload Leveling & Over-Allocation Mitigation | Identify team burnout risks and execute direct task redistribution and drag-and-drop leveling from the capacity chart. | 2.0 hrs
|  | Zoho People Leave Integration & Shift Sync | Integrate individual employee leave schedules and shift timings from Zoho People into automated project completion calculations. | 1.5 hrs
8 | Advanced Timesheets, Multi-Tier Billing & Approvals | Multi-Tier Billing Rates Architecture | Configure Staff-Based, Role-Based, and Project-Based hourly billing rates for accurate client invoicing and costing. | 2.0 hrs
|  | Live Stopwatch Timer & Mobile Tracking | Configure in-app live multi-timer stopwatch and mobile time tracking with automated background work logging. | 1.5 hrs
|  | Multi-Tier Timesheet Approval & Lock Periods | Establish multi-stage approval workflows (PM -> Finance Head) with automated timesheet lockdown at payroll cutoff. | 2.5 hrs
9 | Issue / Bug SLA Management & Business Rules | Custom Issue Layouts, Email-to-Issue & Views | Build custom bug tracking layouts, custom severity matrices, email-to-issue alias, and issue-to-task linking. | 2.0 hrs
|  | SLA Management & Business Rules Auto-Assign | Configure formal SLAs (First Response & Resolution) and automated business rules for auto-assignment and field updates. | 2.0 hrs
|  | Multi-Level Escalation Automation Rules | Automate multi-tier escalation triggers routing SLA-breaching issues to senior leadership via high-priority alerts. | 1.5 hrs
10 | Ecosystem Integrations: Zoho Books, CRM & Office | Direct Zoho Books Timesheet-to-Invoice Sync | Configure bi-directional sync linking Zoho Projects with Zoho Books/Invoice for one-click invoice generation from approved hours. | 2.5 hrs
|  | Zoho CRM Deal-to-Project Auto-Creation | Auto-instantiate project templates upon Deal Won in Zoho CRM, syncing client details, scope deliverables, and target dates. | 2.0 hrs
|  | Google Workspace & Microsoft 365 Integration | Connect Google Drive/Calendar and Microsoft Teams/Outlook/OneDrive/SharePoint with CSV & MS Project (.mpp) migration. | 2.5 hrs
11 | Departmental Training, Simulation & 30-Day Hypercare | Departmental Training Sprints | Deliver specialized training workshops for Project Managers, Resource Planners, and Finance/Billing administrators. | 2.5 hrs
|  | User Acceptance Testing (UAT) Simulation | Simulate 25+ real client delivery scenarios: scope changes, baseline shifts, contractor timesheets, and invoice sync. | 2.0 hrs
|  | 30-Day Post Go-Live Hypercare | Dedicated consultant on-call support during first monthly project closing, client billing run, and resource reviews. | 1.5 hrs
TOTAL ESTIMATED IMPLEMENTATION EFFORT: |  |  |  | 63.0 Hours

## Elite Package
ELITE TECH CORPORATION
Zoho Projects Implementation — Elite Package
Scope Summary: 11 Modules ¦ 34 Activities ¦ Total Estimated Effort: 115.0 Hours ¦ Target Timeline: 30–45 Working Days Enterprise PMO transformation with multi-entity governance, custom Deluge scripting, client & subcontractor portals, Zoho Analytics BI dashboards, EVM, and extended hypercare.
Sno | Module | Activities | Description | Est. Hours
1 | Critical Path Method (CPM), Schedule Risk & Baseline Engine | Critical Path Method (CPM) Optimization | Identify true critical path deliverables, zero-slack tasks, and automated schedule compression options. | 3.0 hrs
|  | Multi-Version Baseline Comparison Engine | Maintain unlimited baseline versions (Original Contract, Approved Scope Change, Revised Schedule) with variance tracking. | 3.0 hrs
|  | Schedule Variance & Buffer Management | Automate slack time tracking, schedule performance index warnings, and delay alerts for program managers. | 2.5 hrs
2 | Multi-Project Resource Forecasting & Capacity Balancing | Multi-Project Resource Capacity Forecasting | Forecast team and department capacity requirements 3 to 6 months in advance based on active and pipeline project commitments. | 3.5 hrs
|  | Multi-Project Resource Balancing & Allocation Rules | Configure cross-project resource utilization views and daily/weekly capacity allocation limits to eliminate multi-project over-commitment. | 3.0 hrs
|  | Resource Cost vs. Billing Margin Yield Analytics | Compare staff cost rates against client billing rates to analyze real-time gross margin and labor yield per team member and department. | 3.0 hrs
3 | Enterprise Project Budgeting & EVM Financial Flow | Multi-Tier Budget Architecture & Baseline Allocation | Setup hierarchical project-level, milestone-level, and task-level budgeting in amount and hours with baseline cost cards and profit margin models. | 3.5 hrs
|  | Real-Time Cost Burn, Expense Ingestion & Margin Tracking | Automate live ingestion of staff timesheet costs and categorized project expenses (direct, subcontractor, overhead) to compute live gross margin burn. | 3.5 hrs
|  | Automated Budget Threshold Escalations & Hard-Stop Freeze | Configure automated multi-tier alert triggers (50%, 80%, 100%) and Deluge/Blueprint hard-stop validation locks halting unapproved work logs upon budget breach. | 3.0 hrs
|  | Earned Value Management (EVM) & Revenue Realization Flow | Configure Planned Value (PV), Earned Value (EV), Actual Cost (AC), CPI, SPI, EAC, and link milestone deliverables to revenue realization in Zoho Books. | 3.0 hrs
4 | Custom Modules Architecture & Enterprise Issue Governance | Custom Modules Setup (Change Requests & Non-Standard Entities) | Build dedicated custom data entities within Zoho Projects (e.g., Change Requests, Submittals, RFI) with custom layouts and relational links. | 3.0 hrs
|  | Multi-Channel Issue / Bug Ingestion & Webhooks | Capture issues and defects via web forms, customer portals, email-to-issue parsers, and external QA webhook pipelines. | 3.0 hrs
|  | Multi-Tier Escalation Hierarchies & Penalty SLA Tracking | Automate strict contractual SLA breach notifications to executives and client representatives with penalty calculation flags. | 2.5 hrs
5 | Multi-Stakeholder Client & Subcontractor Sandboxed Portals | Multi-Tier External Portal Architecture | Configure segmented, secure portal environments for enterprise clients, subcontractors, and freelance specialists. | 3.0 hrs
|  | Subcontractor Task Assignment & Work Logging | Enable external contractors to log task progress and billable hours within restricted project sandboxes without visibility to full scope. | 2.5 hrs
|  | Client Deliverable Sign-Off & Change Order Approval | Build formal change order request workflows requiring client digital approval before scope, budget, or timeline adjustments. | 2.5 hrs
6 | Client Collaboration Portal, Pages (Wiki) & Forums | Branded Client Self-Service Portal | Configure secure client portal access with restricted visibility limited exclusively to designated tasks and milestones. | 2.0 hrs
|  | Client Deliverable Approval Workflows | Enable external client stakeholders to review completed deliverables, approve milestones, or request revisions directly. | 1.5 hrs
|  | Interactive Forums, Pages (Wiki) & Docs | Setup project discussion forums, announcement boards, and interactive Wiki pages for standardized project documentation. | 1.5 hrs
7 | Zoho Ecosystem Deep Interconnect (Desk, People, Sprints) | Zoho Desk Ticket-to-Task / Bug Interconnect | Bi-directional sync converting customer support tickets into project tasks or bugs with live status reflection. | 3.5 hrs
|  | Zoho People Employee Leaves & Resource Calendar Sync | Live two-way sync of employee leave approvals, shifts, and public holidays into project timelines. | 3.5 hrs
|  | Zoho Sprints & Cliq Interactive Channels | Configure hybrid agile sprint syncing with Zoho Sprints and auto-create dedicated Cliq project channels and standups. | 3.0 hrs
8 | Custom Deluge Scripting & Enterprise Workflow Functions | Complex Deluge Business Logic Development | Develop custom Deluge functions for automated parent task completion, dynamic deadline recalculation, and custom rollups. | 5.5 hrs
|  | Cross-Module Data Validation & Auto-Trigger Scripts | Script cross-module data validation rules, automatic milestone unlocks, and project state change triggers. | 4.5 hrs
|  | Custom Notification Bots & Automated Executive Summaries | Build automated Deluge bots sending weekly Slack/Cliq/Email portfolio summaries and risk digests. | 4.0 hrs
9 | Webhooks, REST APIs & DevOps Integrations | GitHub, GitLab & Bitbucket DevOps Integrations | Link code commits, pull requests, and git branches directly to Zoho Projects task IDs with auto-status updates. | 4.0 hrs
|  | Outbound Webhooks & ERP Real-Time Event Streaming | Configure real-time event webhooks pushing project status, milestones, and timesheets to enterprise ERP systems. | 4.0 hrs
|  | Custom REST API Endpoints & Data Connectors | Develop custom API integrations for third-party billing, procurement, or legacy data warehouses. | 3.5 hrs
10 | Zoho Analytics Executive BI & Portfolio Dashboards | Zoho Analytics Deep Sync & Data Modeling | Connect Zoho Projects database to Zoho Analytics with custom relational data tables and query tables. | 4.0 hrs
|  | Executive Portfolio Health & Margin Dashboards | Build interactive BI dashboards showing portfolio health, project profitability, burn rates, and team utilization. | 3.5 hrs
|  | Scheduled C-Suite Reports & KPI Alert Automations | Configure automated PDF/email KPI digests for CEO, PMO Director, and Finance Controller with anomaly alerts. | 3.0 hrs
11 | Enterprise Change Management, UAT & 45-Day Hypercare | Multi-Tier PMO & Team Training Academy | Conduct tailored interactive training academies for PMO leads, Project Managers, and Technical Engineers with recorded video SOPs. | 5.5 hrs
|  | 50+ Scenario End-to-End UAT Simulation | Rigorous simulation covering scope changes, critical path delays, subcontractor billing, and CRM cutover with real enterprise data. | 4.5 hrs
|  | 45-Day Enterprise Hypercare & Post Go-Live Audit | Dedicated Senior Solution Architect on-call for two full billing cycles, project kickoffs, and PMO optimization reviews. | 6.5 hrs
TOTAL ESTIMATED IMPLEMENTATION EFFORT: |  |  |  | 115.0 Hours